## How To Use
Project Resource Sheet 관리
1. New Project Sheet Creation
| A | Temp. V00 sheet를 copy하여 sheet 이름을 수정하여 >< (검정색 화살표) 사이로 sheet를 옮긴다.
| B | 검정색 화살표 사이에 Sheet를 넣으면 자동으로 SheetMerge로 Data가 통합된다.
| C | Temp. V00
|  | * | 연두색 - 입력 혹은 선택 항목
|  | * | 회색 - 자동입력
|  | 1 | Dropdown menu 에서 project를 선택하면 B1의 Project IO / B열 Status / C열 Project 내용이 자동으로 선택된다. - by PMO
|  | 2 | Dropdown menu 에서 Name을 선택하면 D열/E열/F열의 내용이 자동으로 선택된다. - by functions or PMO
|  | 3 | Gate5/Gate6 일정을 기재한다. (년/월 기재) - by PMO
|  | 4 | 월별 HC를 입력한다. - by functions
|  | 5 | 마지막 라인에 전체 project Gate plan 일정을 입력한다. 예) G1, G2….. - by PMO
2. Summary Sheet 설명
| A | SheetMerge |  | Do Not Change Anything | 입력한 project sheet의 모든 값들이 자동으로 통합되는 database sheet
| B | P1_정원 |  | Pivot Sheet | The number of available HC
| C | P2_부서 |  | Pivot Sheet | 정원 대비 forecast demand 차이
| D | P3_PRJ |  | Pivot Sheet | 프로젝트 별 forecast 현황
| F | P3_PRJ engineer gap |  | Pivot Sheet | Project allocation 별 engineer resource gap
| E | P4_Name |  | Pivot Sheet | 부서별 allocation 현황
| G | Project IO |  | Owner only allows changes | Owner - Jinney L | Project status / IO list
| H | 정원 |  | Owner only allows changes | Owner - Jinney L / Mogen S / Dorothy N |  | IS 총인원
99. Revision Note
| Ver. |  | Date | Description
| V1 |  | 2025-07-15 | 양식 변경
| V1.1 |  | 2025-07-15 | Excel Error 복구
| V1.2 |  | 2025-07-23 | PJT Lifecycle
1
2
3
4
5

## 2026 Finance Allocation (hidden)
IO | Project | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
406437 | Tumalo Phase 1_EUV System | 8.15 | 7 | 9.75 | 9.15 | 8.65 | 7.15 | 7.15 | 6.65
407039 | Tumalo Phase 2_EUV System | 10.55 | 10.41 | 11.45 | 11.45 | 11.45 | 11.45 | 11.45 | 13.95 | 13.95 | 13.95 | 13.95 | 13.95
406403 | Hydrogen Recycling System_KR | 0.2 | 0.2
406886 | EUV Gen3 plus/H2D HPD/HRS Config.-A&D | 10.3 | 12 | 10.8 | 10.4 | 10.4 | 10.4 | 8.5 | 8.5 | 8.6 | 8.6 | 8.6 | 7.1
406376 | Kanara Phase 1 EUV Gen4 |  |  | 1 | 2 | 5 | 6 | 6 | 8 | 12 | 12 | 12 | 12
407343 | Hydrogen Recovery System | 7.7 | 10 | 13.35 | 14.75 | 14.75 | 14.75 | 14.15 | 15.15 | 14.85 | 14.85 | 14.85 | 15.35
407060 | CatOx Alpha Design | 0.9 | 0.2
| Total | 37.8 | 39.81 | 46.35 | 47.75 | 50.25 | 49.75 | 47.25 | 52.25 | 49.4 | 49.4 | 49.4 | 48.4
| Total available HC | 42.6 | 38.6 | 39.3 | 39.9 | 39.9 | 39.9 | 39.6 | 39.6 | 39.3 | 40.3 | 44.3 | 44.3 | 45.3 | 45.3 | 44.8 | 44.8 | 44.8 | 44.8 | 44.8 | 54.8 | 44.8 | 44.8 | -2.6
| Balance | 4.8 | -1.21 | -7.05 | -7.85 | -10.35 | -9.85 | -7.65 | -12.65 | -10.1 | -9.1 | -5.1 | -4.1
407154 | LPLN TOP 150 support | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Kanara 포함
IO | Project | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
406437 | Tumalo Phase 1_EUV System | 8.15 | 7 | 8.3 | 7.4 | 6.4 | 6.3 | 5.6 | 5.1
407039 | Tumalo Phase 2_EUV System | 10.55 | 10.41 | 10.4 | 8.8 | 9.8 | 9.8 | 8.8 | 8.8 | 11.4 | 11.4 | 11.4 | 11.4 | 10.4 | 10.4 | 10.4 | 10.4 | 9.9 | 9.9 | 8.3 | 8.3 | 8.3 | 1.25 | 1.25 | 1.25
406403 | Hydrogen Recycling System_KR | 0.2 | 0.2
406886 | EUV Gen3 plus/H2D HPD/HRS Config.-A&D | 10.3 | 12 | 12.1 | 9.4 | 9.4 | 9.4 | 7.9 | 7.4 | 8 | 8 | 8 | 7
406376 | Kanara Phase 1 EUV Gen4 |  |  | 1.1 | 3.8 | 3.8 | 5.4 | 8.9 | 9.9 | 11.1 | 12.1 | 12.1 | 12.6 | 14.1 | 14.1 | 14.1 | 13.1 | 12.6 | 12.6 | 12.4 | 12.2 | 12.2 | 12.2 | 11.7 | 11.7 | 10.3 | 10.3 | 10.3 | 10.3 | 9.8 | 9.8
407343 | Hydrogen Recovery System | 7.7 | 10 | 10.7 | 12.2 | 12.2 | 12.2 | 13.2 | 14.2 | 13.7 | 13.7 | 13.7 | 14.2 | 14.7 | 13.7 | 13.7 | 13.7 | 13.7 | 13.7 | 12.2 | 11.8 | 11.8 | 10.8 | 10.8 | 10.8
407060 | CatOx Alpha Design | 0.9 | 0.2
| Total | 37.8 | 39.81 | 42.6 | 41.6 | 41.6 | 43.1 | 44.4 | 45.4 | 44.2 | 45.2 | 45.2 | 45.2
| Total available HC (현재 IS) | 42.6 | 38.6 | 39.3 | 39.9 | 39.9 | 39.9 | 39.6 | 39.6 | 39.3 | 40.3 | 44.3 | 44.3
| Balance | 4.8 | -1.21 | -3.3 | -1.7 | -1.7 | -3.2 | -4.8 | -5.8 | -4.9 | -4.9 | -0.9 | -0.9
Kanara 미포함
IO | Project | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
406437 | Tumalo Phase 1_EUV System | 8.15 | 7 | 8.3 | 7.4 | 6.4 | 6.3 | 5.6 | 5.1
407039 | Tumalo Phase 2_EUV System | 10.55 | 10.41 | 10.4 | 8.8 | 9.8 | 9.8 | 8.8 | 8.8 | 11.4 | 11.4 | 11.4 | 11.4
406403 | Hydrogen Recycling System_KR | 0.2 | 0.2
406886 | EUV Gen3 plus/H2D HPD/HRS Config.-A&D | 10.3 | 12 | 12.1 | 9.4 | 9.4 | 9.4 | 7.9 | 7.4 | 8 | 8 | 8 | 7
406376 | Kanara Phase 1 EUV Gen4
407343 | Hydrogen Recovery System | 7.7 | 10 | 10.7 | 12.2 | 12.2 | 12.2 | 13.2 | 14.2 | 13.7 | 13.7 | 13.7 | 14.2
407060 | CatOx Alpha Design | 0.9 | 0.2 | [10 empty] | 44.9 | 44.9 | 45.9 | 45.9 | 45.9 | 45.9 | 45.9 | 45.9 | 45.9 | 45.9 | 45.9 | 45.9
| Total | 37.8 | 39.81 | 41.5 | 37.8 | 37.8 | 37.7 | 35.5 | 35.5 | 33.1 | 33.1 | 33.1 | 32.6
| Total available HC | 42.6 | 38.6 | 39.3 | 39.9 | 39.9 | 39.9 | 39.6 | 39.6 | 39.3 | 40.3 | 44.3 | 44.3
| Balance | 4.8 | -1.21 | -2.2 | 2.1 | 2.1 | 2.2 | 4.1 | 4.1 | 6.2 | 7.2 | 11.2 | 11.7
Kanara 조정 - 3월 입력
IO | Project | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
406437 | Tumalo Phase 1_EUV System | 8.15 | 7 | 8.3 | 7.4 | 6.4 | 6.3 | 5.6 | 5.1
407039 | Tumalo Phase 2_EUV System | 10.55 | 10.41 | 10.4 | 8.8 | 9.8 | 9.8 | 8.8 | 8.8 | 11.4 | 11.4 | 11.4 | 11.4
406403 | Hydrogen Recycling System_KR | 0.2 | 0.2
406886 | EUV Gen3 plus/H2D HPD/HRS Config.-A&D | 10.3 | 12 | 12.1 | 9.4 | 9.4 | 9.4 | 7.9 | 7.4 | 8 | 8 | 8 | 7
406376 | Kanara Phase 1 EUV Gen4 |  |  | 1 | 1 | 2 | 2 | 4 | 4 | 6 | 6 | 6 | 8
407343 | Hydrogen Recovery System | 7.7 | 10 | 10.7 | 12.2 | 12.2 | 12.2 | 13.2 | 14.2 | 13.7 | 13.7 | 13.7 | 14.2
407060 | CatOx Alpha Design | 0.9 | 0.2
| Total | 37.8 | 39.81 | 42.5 | 38.8 | 39.8 | 39.7 | 39.5 | 39.5 | 39.1 | 39.1 | 39.1 | 40.6
| Total available HC | 42.6 | 38.6 | 39.3 | 39.9 | 39.9 | 39.9 | 39.6 | 39.6 | 39.3 | 40.3 | 44.3 | 44.3
| Balance | 4.8 | -1.21 | -3.2 | 1.1 | 0.1 | 0.2 | 0.1 | 0.1 | 0.2 | 1.2 | 5.2 | 3.7

## Temp. V00
|  |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-09 | SUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | PJT Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 |  |  | 0 | Engineering | * Manager | * Eng Manager | JiYoung Son
2 |  |  | 0 | PMO | * Manager | * Manager | Jinney Lee
3 |  |  | 0 | PMO | PM | PM | Project manager
4 |  |  | 0 | NPI IS | * Manager | * Manager | Dorothy Noh
5 |  |  | 0 | NPI IS | System 1 | Tech Lead | Tech Lead
6 |  |  | 0 | NPI IS | System 1 | System engineer | System engineer
7 |  |  | 0 | NPI IS | System 1 | Service engineer | Service engineer
8 |  |  | 0 | NPI IS | Mechanical | Leader | Jeremy Park
9 |  |  | 0 | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer
10 |  |  | 0 | Control Eng. | * Manager | * Manager | Mogen Seo
11 |  |  | 0 | Control Eng. | Software | Leader | Gerald Park
12 |  |  | 0 | Control Eng. | Software | Software engineer | Software engineer
13 |  |  | 0 | Control Eng. | Software | SW test engineer | SW test engineer
14 |  |  | 0 | Control Eng. | Electrical | Leader | Joshua Im
15 |  |  | 0 | Control Eng. | Electrical | Electrical engineer | Electrical engineer
16 |  |  | 0 | - | - | -
17 |  |  | 0
18 |  |  | 0
19 |  |  | 0 |  |  |  | Gate Plan |  |  | G2 |  |  | G5 |  | G6

## SheetMerge
No | Status | PJT Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Cancelled | Cancelled | Ganymede support - PCCA | NPI IS | System 1 | System engineer | System engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | Software engineer | Ashley Yun | 0 | 0 | 0 | 0.3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
3 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | Software engineer | Rachel Bae | 0 | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
4 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | SW test engineer | Amelia An | 0 | 0 | 1 | 1 | 0.9 | 0.7 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
5 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | Software engineer | Roy Choi | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | SW test engineer | Moonsu Cho | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0
7 | Active | Planning | Unify support | Control Eng. | Software | Leader | Gerald Park | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0
8 | Active | Planning | Unify support | Control Eng. | Software | Software engineer | Rachel Bae | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Active | Planning | Unify support | Control Eng. | Software | SW test engineer | Amelia An | 0 | 0 | 0 | 0 | 0.1 | 0.3 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Active | Complete | R&D General - Legacy/TSG | NPI IS | System 1 | Technician | Robin Park | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Active | Lead | CatOX Alpha design | NPI IS | Mechanical | Mechanical engineer | Jiny Park | 0 | 0 | 0 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Cancelled | Cancelled | Hermes | Control Eng. | Software | Software engineer | Roy Choi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Cancelled | Cancelled | Hermes | Control Eng. | Software | SW test engineer | Moonsu Cho | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Active | Active | LPLN TOP 150 support | NPI IS | System 3 | Tech Lead | Grace Ji | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Active | Active | LPLN TOP 150 support | NPI IS | System 1 | System engineer | Ricky Kim | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Active | Active | LPLN TOP 150 support | NPI IS | System 1 | Service engineer | Chan Hwang | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Active | Active | LPLN TOP 150 support | NPI IS | System 1 | Service engineer | Judy Lee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Active | Active | Micron A&D | PMO | * Manager | * Manager | Jinney Lee | 2026-08-28 | 2026-12-18 | 0.2 | 0.2 | 0.2 | 0.25 | 0.25 | 0.25 | 0.25 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active | Active | Micron A&D | PMO | PM | PM | Eugene Lee | 2026-08-28 | 2026-12-18 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.1 | 0.9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Active | Active | Micron A&D | NPI IS | * Manager | * Manager | Dorothy Noh | 2026-08-28 | 2026-12-18 | 0.2 | 0.2 | 0.2 | 0.25 | 0.25 | 0.25 | 0.25 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Active | Active | Micron A&D | NPI IS | Mechanical | Leader | Jeremy Park | 2026-08-28 | 2026-12-18 | 0.2 | 0.3 | 0.3 | 0.25 | 0.25 | 0.25 | 0.25 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Active | Active | Micron A&D | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2026-08-28 | 2026-12-18 | 1 | 1 | 1 | 0.5 | 0 | 0 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Active | Active | Micron A&D | NPI IS | Mechanical | Mechanical engineer | Jiny Park | 2026-08-28 | 2026-12-18 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Active | Active | Micron A&D | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | 2026-08-28 | 2026-12-18 | 0 | 0 | 1 | 0.2 | 0 | 0 | 1 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Active | Active | Micron A&D | NPI IS | System 2 | Tech Lead | Chad Seo | 2026-08-28 | 2026-12-18 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Active | Active | Micron A&D | NPI IS | System 2 | Tech Lead | Emma Kim | 2026-08-28 | 2026-12-18 | 1 | 1 | 1 | 0.7 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Active | Active | Micron A&D | NPI IS | System 2 | System engineer | Jess Kim | 2026-08-28 | 2026-12-18 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Active | Active | Micron A&D | NPI IS | System 3 | System engineer | Tred Park | 2026-08-28 | 2026-12-18 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Active | Active | Micron A&D | NPI IS | System 2 | System engineer | Stella Lim | 2026-08-28 | 2026-12-18 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Active | Active | Micron A&D | NPI IS | System 2 | System engineer | Harry Kwak | 2026-08-28 | 2026-12-18 | 1 | 1 | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Active | Active | Micron A&D | Engineering | * Manager | * Eng Manager | JiYoung Son | 2026-08-28 | 2026-12-18 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Active | Active | Micron A&D | Control Eng. | * Manager | * Manager | Mogen Seo | 2026-08-28 | 2026-12-18 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Active | Active | Micron A&D | Control Eng. | Electrical | Leader | Joshua Im | 2026-08-28 | 2026-12-18 | 0.3 | 0.3 | 0.3 | 0.25 | 0.25 | 0.25 | 0.25 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Active | Active | Micron A&D | Control Eng. | Electrical | Electrical engineer | Dean Choi | 2026-08-28 | 2026-12-18 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Active | Active | Micron A&D | Control Eng. | Software | Leader | Gerald Park | 2026-08-28 | 2026-12-18 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Active | Active | Micron A&D | Control Eng. | Software | Software engineer | Roy Choi | 2026-08-28 | 2026-12-18 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.3 | 0.7 | 0.7 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Active | Active | Micron A&D | Control Eng. | Software | SW test engineer | Moonsu Cho | 2026-08-28 | 2026-12-18 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Active | Active | Micron A&D | NPI IS | System 1 | System engineer | Chloe Jeong | 2026-08-28 | 2026-12-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Active | Active | Micron A&D | NPI IS | System 2 | System engineer | Kevin Ko | 2026-08-28 | 2026-12-18 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Active | Active | Micron A&D | Central Engineering | Reliability | Reliability lead | Victor Do | 2026-08-28 | 2026-12-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Active | Active | Micron A&D | - | - | - | Gate Plan | 2026-08-28 | 2026-12-18 | 0 | Update | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Active | Active | Tumalo Ph2 | Engineering | * Manager | * Eng Manager | Jiyoung Son | 2026-04-01 | 2026-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active | Active | Tumalo Ph2 | PMO | * Manager | * Manager | Jinney Lee | 2026-04-01 | 2026-09-28 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Active | Active | Tumalo Ph2 | PMO | PM | PM | Evan Lee | 2026-04-01 | 2026-09-28 | 0 | 0.5 | 0.5 | 0.8 | 0.8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Active | Active | Tumalo Ph2 | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-04-01 | 2027-09-28 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | Tech Lead | Jacob Lee | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | Tech Lead | William Lee | 2027-04-01 | 2027-09-28 | 0 | 0.9 | 0.9 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Active | Active | Tumalo Ph2 | NPI IS | System 2 | System engineer | Harry Kwak | 2027-04-01 | 2027-09-28 | 0 | 0 | 0.4 | 0.4 | 0 | 0 | 0.4 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | System engineer | Noah Yeom | 2027-04-01 | 2027-09-28 | 0 | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | System engineer | Alyssa Park | 2027-04-01 | 2027-09-28 | 0 | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | System engineer | Anders You | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | Service engineer | Fred Lee | 2027-04-01 | 2027-09-28 | 0 | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | Service engineer | Chan Hwang | 2027-04-01 | 2027-09-28 | 0 | 0 | 0.4 | 0.4 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Active | Active | Tumalo Ph2 | NPI IS | System 2 | System engineer | Kevin Ko | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | System engineer | Chloe Jeong | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | Technician | Robin Park | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Leader | Jeremy Park | 2027-04-01 | 2027-09-28 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Allie Park | 2027-04-01 | 2027-09-28 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Wayne Jo | 2027-04-01 | 2027-09-28 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Active | Active | Tumalo Ph2 | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-04-01 | 2027-09-28 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Leader | Gerald Park | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Software engineer | Ethan Jung | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Software engineer | Roy Choi | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Active | Active | Tumalo Ph2 | Control Eng. | Software | SW test engineer | Dave Kim | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Active | Active | Tumalo Ph2 | Control Eng. | Software | SW test engineer | Moonsu Cho | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Software engineer | Owen Rim | 2027-04-01 | 2027-09-28 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Leader | Joshua Im | 2027-04-01 | 2027-09-28 | 0 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Electrical engineer | May Kwon | 2027-04-01 | 2027-09-28 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Electrical engineer | Dean Choi | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Electrical engineer | Andy Jang | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Active | Active | Tumalo Ph2 | - | - | - | Gate Plan | 2027-04-01 | 2027-09-28 | 0 | G2 | 0 | 0 | 0 | 0 | 0 | 0 | G3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G4 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Active | 0 | Tumalo Ph1 | Engineering | * Manager | * Eng Manager | Jiyoung Son | 2026-02-01 | 2026-08-30 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active | 0 | Tumalo Ph1 | PMO | * Manager | * Manager | Jinney Lee | 2026-02-01 | 2026-08-30 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Active | 0 | Tumalo Ph1 | PMO | PM | PM | Yuro Lee | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.7 | 0.7 | 0.7 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Active | Active | Tumalo Ph1 | NPI IS | * Manager | * Manager | Dorothy Noh | 2026-02-01 | 2026-08-30 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | Tech Lead | Jacob Lee | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | Tech Lead | Grace Ji | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | Tech Lead | William Lee | 2026-03-01 | 2026-09-27 | 0 | 0 | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Active | Active | Tumalo Ph1 | NPI IS | System 2 | System engineer | Harry Kwak | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.5 | 0.5 | 0.6 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | System engineer | Alyssa Park | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | System engineer | Noah Yeom | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Active | Active | Tumalo Ph1 | NPI IS | System 1 | System engineer | Anders You | 2026-02-01 | 2026-08-30 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | Service engineer | Fred Lee | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Active | Active | Tumalo Ph1 | NPI IS | System 1 | Service engineer | Chan Hwang | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Active | Active | Tumalo Ph1 | NPI IS | System 1 | Technician | Robin Park | 2026-02-01 | 2026-08-30 | 0.8 | 0.8 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Leader | Jeremy Park | 2026-02-01 | 2026-08-30 | 0.3 | 0.3 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Mechanical engineer | Evan Yu | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Mechanical engineer | Wayne Jo | 2026-02-01 | 2026-08-30 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Mechanical engineer | Esther Jeong | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Mechanical engineer | Allie Park | 2026-02-01 | 2026-08-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Active | Active | Tumalo Ph1 | Control Eng. | * Manager | * Manager | Mogen Seo | 2026-02-01 | 2026-08-30 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Leader | Gerald Park | 2026-02-01 | 2026-08-30 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Ethan Jung | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Roy Choi | 2026-02-01 | 2026-08-30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Ashley Yun | 2026-02-01 | 2026-08-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Rachel Bae | 2026-02-01 | 2026-08-30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Active | Active | Tumalo Ph1 | Control Eng. | Software | SW test engineer | Dave Kim | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Active | Active | Tumalo Ph1 | Control Eng. | Software | SW test engineer | Moonsu Cho | 2026-02-01 | 2026-08-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Active | Active | Tumalo Ph1 | Control Eng. | Software | SW test engineer | Amelia An | 2026-02-01 | 2026-08-30 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Leader | Joshua Im | 2026-02-01 | 2026-08-30 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Electrical engineer | May Kwon | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Electrical engineer | Julia Mun | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Electrical engineer | Andy Jang | 2026-02-01 | 2026-08-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Active | Active | Tumalo Ph1 | - | - | - | Gate Plan | 2026-02-01 | 2026-08-30 | 0 | 0 | G4 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Active | Active | Hydrogen Recovery System-7N | Engineering | * Manager | * Eng Manager | JiYoung Son | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active | Active | Hydrogen Recovery System-7N | PMO | * Manager | * Manager | Jinney Lee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Active | Active | Hydrogen Recovery System-7N | PMO | PM | PM | Yuro Lee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Active | Active | Hydrogen Recovery System-7N | NPI IS | * Manager | * Manager | Dorothy Noh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Active | Active | Hydrogen Recovery System-7N | NPI IS | System 2 | Tech Lead | Emma Kim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Active | Active | Hydrogen Recovery System-7N | NPI IS | System 2 | System engineer | Kevin Ko | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Active | Active | Hydrogen Recovery System-7N | NPI IS | System 1 | System engineer | System engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Active | Active | Hydrogen Recovery System-7N | NPI IS | System 2 | Service engineer | Sophie Kim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Active | Active | Hydrogen Recovery System-7N | NPI IS | Mechanical | Leader | Jeremy Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Active | Active | Hydrogen Recovery System-7N | NPI IS | Mechanical | Mechanical engineer | Sooyoung Song | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Active | Active | Hydrogen Recovery System-7N | NPI IS | Mechanical | Mechanical engineer | Jiny Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Active | Active | Hydrogen Recovery System-7N | NPI IS | Mechanical | Mechanical engineer | Jayce Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Active | Active | Hydrogen Recovery System-7N | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | * Manager | * Manager | Mogen Seo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | Software | Leader | Gerald Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | Software | Software engineer | Software engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | Software | SW test engineer | Moonsu Cho | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | Electrical | Leader | Joshua Im | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | Electrical | Electrical engineer | Hana Lee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Active | Active | Hydrogen Recovery System-7N | NPI IS | System 2 | System engineer | Harry Kwak | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Active | Active | Hydrogen Recovery System-7N | NPI IS | System 1 | Tech Lead | Michael Kim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | Software | Software engineer | Owen Rim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | Software | SW test engineer | Amelia An | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Active | Active | Hydrogen Recovery System-7N | - | - | - | Gate Plan | 7N | 0 | G2 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G3 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Active | Active | Hydrogen Recovery System-7N | - | - | - | Gate Plan | 9N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G3 | Build | Test | Test | 0 | 0 | G4 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Active | Opportunty | Kanara | Engineering | * Manager | * Eng Manager | JiYoung Son | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active | Opportunty | Kanara | PMO | * Manager | * Manager | Jinney Lee | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
3 | Active | Opportunty | Kanara | PMO | PM | PM | Project manager | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
4 | Active | Opportunty | Kanara | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
5 | Active | Opportunty | Kanara | NPI IS | System 3 | Tech Lead | Jacob Lee | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
6 | Active | Opportunty | Kanara | NPI IS | System 3 | System engineer | Tred Park | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
7 | Active | Opportunty | Kanara | NPI IS | System 1 | System engineer | System engineer | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
8 | Active | Opportunty | Kanara | NPI IS | System 1 | System engineer | Chloe Jeong | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
9 | Active | Opportunty | Kanara | NPI IS | System 1 | Service engineer | Service engineer | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Active | Opportunty | Kanara | NPI IS | Mechanical | Leader | Jeremy Park | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
12 | Active | Opportunty | Kanara | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
13 | Active | Opportunty | Kanara | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
14 | Active | Opportunty | Kanara | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Active | Opportunty | Kanara | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
16 | Active | Opportunty | Kanara | Control Eng. | Software | Leader | Gerald Park | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Active | Opportunty | Kanara | Control Eng. | Software | Software engineer | Ethan Jung | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
18 | Active | Opportunty | Kanara | Control Eng. | Software | SW test engineer | Dave Kim | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
19 | Active | Opportunty | Kanara | Control Eng. | Electrical | Leader | Joshua Im | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
20 | Active | Opportunty | Kanara | Control Eng. | Electrical | Electrical engineer | Julia Mun | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
21 | Active | Opportunty | Kanara | Control Eng. | Electrical | Electrical engineer | Andy Jang | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Active | Opportunty | Kanara | Control Eng. | Software | Software engineer | Software engineer | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Active | Opportunty | Kanara | - | - | - | Gate Plan | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G1 | 0 | 0 | 0 | 0 | G2 | 0 | 0 | 0 | 0 | G3 | 0 | 0 | 0 | 0 | 0 | 0 | G4 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0
1 | Plan | Lead | SAVAS | Engineering | * Manager | * Eng Manager | JiYoung Son | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Plan | Lead | SAVAS | PMO | * Manager | * Manager | Jinney Lee | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Plan | Lead | SAVAS | PMO | PM | PM | Project Manager | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Plan | Lead | SAVAS | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Plan | Lead | SAVAS | NPI IS | System 1 | Tech Lead | Tech Lead | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Plan | Lead | SAVAS | NPI IS | System 1 | System engineer | System engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Plan | Lead | SAVAS | NPI IS | System 1 | System engineer | System engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Plan | Lead | SAVAS | NPI IS | System 1 | System engineer | System engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Plan | Lead | SAVAS | NPI IS | System 1 | Service engineer | Service engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Plan | Lead | SAVAS | NPI IS | Mechanical | Leader | Jeremy Park | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Plan | Lead | SAVAS | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Plan | Lead | SAVAS | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Plan | Lead | SAVAS | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Plan | Lead | SAVAS | Control Eng. | Software | Leader | Gerald Park | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Plan | Lead | SAVAS | Control Eng. | Software | Software engineer | Software engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Plan | Lead | SAVAS | Control Eng. | Software | Software engineer | Software engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Plan | Lead | SAVAS | Control Eng. | Software | SW test engineer | SW test engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Plan | Lead | SAVAS | Control Eng. | Electrical | Leader | Joshua Im | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Plan | Lead | SAVAS | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Plan | Lead | SAVAS | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Plan | Lead | SAVAS | - | - | - | Gate Plan | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G1 | 0 | 0 | G2 | 0 | 0 | 0 | 0 | G3 | 0 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | potential | Lead | HRS 9N Upgarde | PMO | * Manager | * Manager | Jinney Lee | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | potential | Lead | HRS 9N Upgarde | PMO | PM | PM | Eugene Lee | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | potential | Lead | HRS 9N Upgarde | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | potential | Lead | HRS 9N Upgarde | NPI IS | System 2 | Tech Lead | Chad Seo | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | potential | Lead | HRS 9N Upgarde | NPI IS | System 1 | System engineer | Anders You | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | potential | Lead | HRS 9N Upgarde | NPI IS | System 3 | Service engineer | Fred Lee | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | potential | Lead | HRS 9N Upgarde | NPI IS | Mechanical | Leader | Jeremy Park | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | potential | Lead | HRS 9N Upgarde | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | potential | Lead | HRS 9N Upgarde | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | potential | Lead | HRS 9N Upgarde | Control Eng. | Software | Leader | Gerald Park | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | potential | Lead | HRS 9N Upgarde | Control Eng. | Software | Software engineer | Software engineer | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | potential | Lead | HRS 9N Upgarde | Control Eng. | Software | SW test engineer | SW test engineer | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | potential | Lead | HRS 9N Upgarde | Control Eng. | Electrical | Leader | Joshua Im | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | potential | Lead | HRS 9N Upgarde | Control Eng. | Electrical | Electrical engineer | Dean Choi | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | potential | Lead | HRS 9N Upgarde | - | - | - | Gate Plan | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G2 | 0 | 0 | 0 | 0 | 0 | Update | 0 | 0 | 0 | 0 | G5/G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | potential | Lead | CatOX | Engineering | * Manager | * Eng Manager | JiYoung Son | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | potential | Lead | CatOX | PMO | * Manager | * Manager | Jinney Lee | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1
3 | potential | Lead | CatOX | PMO | PM | PM | Yuro Lee | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4 | potential | Lead | CatOX | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0
5 | potential | Lead | CatOX | NPI IS | System 1 | Tech Lead | Michael Kim | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | potential | Lead | CatOX | NPI IS | System 1 | System engineer | System engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | potential | Lead | CatOX | NPI IS | System 1 | System engineer | System engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
8 | potential | Lead | CatOX | NPI IS | System 1 | System engineer | System engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | potential | Lead | CatOX | NPI IS | System 1 | Service engineer | Service engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
10 | potential | Lead | CatOX | NPI IS | Mechanical | Leader | Jeremy Park | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0
11 | potential | Lead | CatOX | NPI IS | Mechanical | Mechanical engineer | Jiny Park | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
12 | potential | Lead | CatOX | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
13 | potential | Lead | CatOX | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
14 | potential | Lead | CatOX | Control Eng. | Software | Leader | Gerald Park | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | potential | Lead | CatOX | Control Eng. | Software | Software engineer | Software engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
16 | potential | Lead | CatOX | Control Eng. | Software | Software engineer | Software engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
17 | potential | Lead | CatOX | Control Eng. | Software | SW test engineer | SW test engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
18 | potential | Lead | CatOX | Control Eng. | Electrical | Leader | Joshua Im | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0
19 | potential | Lead | CatOX | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
20 | potential | Lead | CatOX | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
21 | potential | Lead | CatOX | - | - | - | Gate Plan | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G1 | 0 | G2 | 0 | 0 | 0 | G3 | 0 | 0 | 0 | 0 | G4 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0
1 | Do Not Use | Active | HRS Integrates | PMO | * Manager | * Manager | Jinney Lee | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Do Not Use | Active | HRS Integrates | PMO | PM | PM | Eugene Lee | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.9 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Do Not Use | Active | HRS Integrates | NPI IS | * Manager | * Manager | Dorothy Noh | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Do Not Use | Active | HRS Integrates | NPI IS | System 2 | Tech Lead | Chad Seo | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Do Not Use | Active | HRS Integrates | NPI IS | System 3 | Tech Lead | William Lee | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Do Not Use | Active | HRS Integrates | NPI IS | System 2 | Tech Lead | Emma Kim | 2026-03-30 | 2026-03-30 | 0 | 0 | 0 | 0.3 | 0.9 | 0.9 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Do Not Use | Active | HRS Integrates | NPI IS | System 2 | Service engineer | Sophie Kim | 2026-03-30 | 2026-03-30 | 0 | 0 | 0 | 0.3 | 1 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Do Not Use | Active | HRS Integrates | NPI IS | System 2 | System engineer | Kevin Ko | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Do Not Use | Active | HRS Integrates | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | 2026-03-30 | 2026-03-30 | 0 | 0 | 0 | 0.3 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Do Not Use | Active | HRS Integrates | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2026-03-30 | 2026-03-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Do Not Use | Active | HRS Integrates | Control Eng. | Electrical | Electrical engineer | Dean Choi | 2026-03-30 | 2026-03-30 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Do Not Use | Active | HRS Integrates | Control Eng. | Software | SW test engineer | Moonsu Cho | 2026-03-30 | 2026-03-30 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Do Not Use | Active | HRS Integrates | NPI IS | System 2 | System engineer | Harry Kwak | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Do Not Use | Active | HRS Integrates | PMO | PM | PM | Yuro Lee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Do Not Use | Active | HRS Integrates | - | - | - | Gate Plan | 2026-03-30 | 2026-03-30 | G2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Complete | Complete | Havasu | Engineering | * Manager | * Eng Manager | Jiyoung Son | 2025-06-25 | 2025-12-22 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Complete | Complete | Havasu | PMO | * Manager | * Manager | Jinney Lee | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Complete | Complete | Havasu | PMO | PM | PM | Evan Lee | 2025-06-25 | 2025-12-22 | 1 | 1 | 0.5 | 0.2 | 0.2 | 0.2 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Complete | Complete | Havasu | NPI IS | * Manager | * Manager | Dorothy Noh | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Complete | Complete | Havasu | NPI IS | System 1 | Tech Lead | Michael Kim | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 0.5 | 0.5 | 0.7 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Complete | Complete | Havasu | NPI IS | System 1 | System engineer | Ricky Kim | 2025-06-25 | 2025-12-22 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Complete | Complete | Havasu | NPI IS | System 1 | System engineer | Anders You | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Complete | Complete | Havasu | NPI IS | System 1 | System engineer | Chloe Jeong | 2025-06-25 | 2025-12-22 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Complete | Complete | Havasu | NPI IS | System 1 | Service engineer | Judy Lee | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 0.5 | 0.5 | 0.7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Complete | Complete | Havasu | NPI IS | Mechanical | Leader | Jeremy Park | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Complete | Complete | Havasu | NPI IS | Mechanical | Mechanical engineer | Sooyoung Song | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Complete | Complete | Havasu | Control Eng. | * Manager | * Manager | Mogen Seo | 2025-06-25 | 2025-12-22 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Complete | Complete | Havasu | Control Eng. | Software | Leader | Gerald Park | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Complete | Complete | Havasu | Control Eng. | Software | Software engineer | Roy choi | 2025-06-25 | 2025-12-22 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Complete | Complete | Havasu | Control Eng. | Software | SW test engineer | Moonsu Cho | 2025-06-25 | 2025-12-22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Complete | Complete | Havasu | Control Eng. | Electrical | Leader | Joshua Im | 2025-06-25 | 2025-12-22 | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Complete | Complete | Havasu | Control Eng. | Electrical | Electrical engineer | Andy Jang | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0.5 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Complete | Complete | Havasu | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2025-06-25 | 2025-12-22 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Complete | Complete | Havasu | - | - | - | Gate plan | 2025-06-25 | 2025-12-22 | G5 | 0 | 0 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | PMO | * Manager | * Manager | Jinney Lee | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | Tech Lead | Chad Seo | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | * Manager | * Manager | Dorothy Noh | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | System engineer | Kevin Ko | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | Service engineer | Sophie Kim | 0 | 0 | 0 | 0 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | System engineer | Jess Kim | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | Mechanical | Leader | Jeremy Park | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | * Manager | * Manager | Mogen Seo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Software | Leader | Gerald Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Software | Software engineer | Ashley Yun | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Software | SW test engineer | Moonsu Cho | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Electrical | Leader | Joshua Im | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Electrical | Electrical engineer | Dean Choi | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 3 | System engineer | Tred Park | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | - | - | - | Gate Plan | 0 | 0 | 0 | 0 | G2 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Complete | Launched | EUV Zenith Plus | PMO | * Manager | * Manager | Jinney Lee | 2025-11-30 | 2026-06-30 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Complete | Launched | EUV Zenith Plus | PMO | PM | PM | Yuro Lee | 2025-11-30 | 2026-06-30 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Complete | Launched | EUV Zenith Plus | NPI IS | * Manager | * Manager | Dorothy Noh | 2025-11-30 | 2026-06-30 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Complete | Launched | EUV Zenith Plus | - | - | - | Gate Plan | 2025-11-30 | 2026-06-30 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Cancelled | Lead | Carl Zeiss | PMO | * Manager | * Manager | Jinney Lee | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Cancelled | Lead | Carl Zeiss | PMO | PM | PM | Project manager | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Cancelled | Lead | Carl Zeiss | NPI IS | * Manager | * Manager | Dorothy Noh | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Cancelled | Lead | Carl Zeiss | NPI IS | System 1 | Tech Lead | Michael Kim | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Cancelled | Lead | Carl Zeiss | NPI IS | System 1 | System engineer | System engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Cancelled | Lead | Carl Zeiss | NPI IS | System 1 | Service engineer | Judy Lee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Cancelled | Lead | Carl Zeiss | NPI IS | Mechanical | Leader | Jeremy Park | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Cancelled | Lead | Carl Zeiss | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Cancelled | Lead | Carl Zeiss | Control Eng. | * Manager | * Manager | Mogen Seo | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Cancelled | Lead | Carl Zeiss | Control Eng. | Software | Leader | Gerald Park | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Cancelled | Lead | Carl Zeiss | Control Eng. | Software | Software engineer | Software engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Cancelled | Lead | Carl Zeiss | Control Eng. | Software | SW test engineer | SW test engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Cancelled | Lead | Carl Zeiss | Control Eng. | Electrical | Leader | Joshua Im | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Cancelled | Lead | Carl Zeiss | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Cancelled | Lead | Carl Zeiss | - | - | - | Gate Plan | 0 | 0 | 0 | 0 | 0 | 0 | G2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## P3_PRJ total gap
| 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-May | Sum of 27-Jun | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec | 0 | 0
Total HC VS Plan | 48.4 | 48.4 | 48.4 | 42.9 | 35.9 | 35.9 | 34.4 | 30.9 | 30.9 | 30.9 | 29.9 | 30.9 | 29.9 | 30.7 | 31.7 | 31.6 | 32.5 | 32.5 | 32.5 | 47.4 | 47.4
Total HC | 48.4 | 48.4 | 48.4 | 44.4 | 45.4 | 45.4 | 45.4 | 45.4 | 45.4 | 45.4 | 45.4 | 46.4 | 46.4 | 46.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4
Status | (Multiple Items)
Resource Role | (All)
Row Labels | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-May | Sum of 27-Jun | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
CatOX Alpha design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Micron A&D | 10.3 | 12.3 | 12.1 | 9.4 | 9.4 | 9.4 | 7.9 | 7.4 | 8 | 8 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R&D General - Legacy/TSG | 1.8 | 1.8 | 2.1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
Tumalo Ph1 | 8.6 | 8.6 | 8.3 | 7.4 | 6.4 | 6.3 | 5.6 | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tumalo Ph2 | 10.7 | 10.7 | 10.4 | 8.8 | 9.8 | 9.8 | 8.8 | 8.8 | 11.4 | 11.4 | 11.4 | 11.4 | 10.4 | 10.4 | 9.9 | 9.9 | 1.25 | 1.25 | 1.25
Unify support | 0.9 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
LPLN TOP 150 support | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kanara | 0 | 0.6 | 1.1 | 3.8 | 3.8 | 5.4 | 8.9 | 9.9 | 11.1 | 12.1 | 12.1 | 12.6 | 14.1 | 14.1 | 12.6 | 12.6 | 12.2 | 11.7 | 11.7
Hydrogen Recovery System-7N | 9.7 | 10.3 | 10.7 | 12.2 | 12.2 | 12.2 | 13.2 | 14.2 | 13.7 | 13.7 | 13.7 | 14.2 | 14.7 | 13.7 | 13.7 | 13.7 | 10.8 | 10.8 | 10.8
SAVAS | 0 | 0 | 0 | 1.5 | 9.5 | 9.5 | 11 | 14.5 | 14.5 | 14.5 | 15.5 | 15.5 | 16.5 | 15.7 | 15.7 | 15.8 | 14.9 | 14.9 | 14.9
Control Eng. | 0 | 0 | 0 | 0 | 2.3 | 2.3 | 2.3 | 3.3 | 3.3 | 3.3 | 4.3 | 4.3 | 4.3 | 4.5 | 4.5 | 4.5 | 4.6 | 4.6 | 4.6
Engineering | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
NPI IS | 0 | 0 | 0 | 0.7 | 5.4 | 5.4 | 6.9 | 9.4 | 9.4 | 9.4 | 9.4 | 9.4 | 10.4 | 9.4 | 9.4 | 9.5 | 8.5 | 8.5 | 8.5
PMO | 0 | 0 | 0 | 0.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7
- | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | 46 | 49 | 48.7 | 48.6 | 56.6 | 58.1 | 60.9 | 65.4 | 64.8 | 65.8 | 66.8 | 66.8 | 57.8 | 56 | 54.5 | 54.6 | 41.75 | 41.25 | 41.25

## P3_PRJ engineer gap
Total HC VS Plan | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | Sum of 26-Sep | Sum of 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | 합계 : 27-Mar | 합계 : 27-Apr | Sum of 27-May | Sum of 27-Jun | 합계 : 27-Jul | 합계 : 27-Aug | 합계 : 27-Sep | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec | 0 | 0
Electrical engineer | 0 | 0 | 0 | 0 | -1 | -1 | -1 | -1.5 | -1.5 | -1.5 | -1.5 | -1.5 | -1.5 | -1.5 | -1.5 | -1.5 | -1.5 | -1.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | -0.5 | 0 | 0
Mechanical engineer | 2 | 1 | 1 | 0 | 0 | -1 | -2 | -4 | -4 | -4 | -4 | -4 | -3 | -2 | -2 | -2 | -2 | -2 | -1.5 | -1.5 | -1.5 | 1.5 | 1.5 | 1.5 | 0 | 0
PM | -1 | -1 | -1 | -1.7 | -2.7 | -3.2 | -3 | -3 | -2.5 | -2.5 | -2.5 | -2.5 | -1.5 | -1.5 | -1.5 | -1.5 | -0.5 | -0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0
Service engineer | 0 | 0 | 0 | 0 | 0 | 0 | -1.5 | -1.5 | -1.5 | -2.5 | -2.5 | -2.5 | -0.5 | -0.5 | -0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 10.5 | 0.5 | 0.5 | 0 | 0
Software engineer | -1 | -1 | -1 | -1 | -2 | -2 | -3 | -3.5 | -3.5 | -3.5 | -3.5 | -3.5 | -3.5 | -3.5 | -3 | -3 | -3 | -3 | -3 | -3 | -3 | -2.5 | -2 | -2 | 0 | 0
SW test engineer | 0 | 0 | 0 | -0.3 | -0.3 | -0.3 | -0.3 | -0.3 | -0.3 | -0.3 | -1.3 | -1.3 | -0.8 | -0.8 | -0.8 | -0.8 | -0.8 | -0.8 | -0.8 | -0.8 | -0.8 | -0.3 | -0.3 | -0.3 | 0 | 0
System engineer | 1 | 0 | 0 | -0.5 | -3 | -3 | -2.5 | -4 | -4 | -4 | -4 | -3 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -1 | -1 | 1 | 1 | 1 | 0 | 0
Tech Lead | 0.6 | 0.1 | 0.1 | -0.5 | -1.5 | -1.5 | -1.5 | -1.5 | -1.5 | -1.5 | -1.5 | -1.5 | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 2 | 2 | 2 | 3 | 3 | 3 | 0 | 0
Technician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | 1.6 | -0.9 | -0.9 | -4 | -10.5 | -12 | -14.8 | -19.3 | -18.8 | -19.8 | -20.8 | -19.8 | -12.3 | -10.3 | -9.8 | -8.8 | -7.8 | -7.8 | -5.3 | -4.3 | -4.3 | 13.2 | 3.7 | 3.7 | 0 | 0
Available engineering HC | 35.3 | 35.5 | 36.2 | 32.2 | 32.9 | 33.5 | 33.5 | 36.5 | 36.2 | 36.2 | 35.9 | 35.9 | 39.9 | 39.9 | 39.9 | 39.9 | 39.4 | 39.4 | 39.4 | 39.4 | 39.4 | 39.4 | 39.4 | 39.4 | 0
Required resource | 40.4 | 42.9 | 42.9 | 42 | 49.5 | 51 | 53.8 | 58.3 | 57.8 | 58.8 | 59.8 | 59.8 | 52.3 | 50.3 | 50.8 | 49.8 | 48.8 | 48.8 | 46.3 | 45.3 | 45.3 | 37.8 | 37.3 | 37.3
Functional Engineer Requirement
Resource Department | (All)
Status | (Multiple Items)
PJT Lifecycle | (All)
Project | (All)
Row Labels | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | Sum of 26-Sep | Sum of 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | 합계 : 27-Mar | 합계 : 27-Apr | Sum of 27-May | Sum of 27-Jun | 합계 : 27-Jul | 합계 : 27-Aug | 합계 : 27-Sep | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
Electrical engineer | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5
Mechanical engineer | 5 | 6 | 6 | 6 | 7 | 8 | 9 | 11 | 11 | 11 | 11 | 11 | 10 | 9 | 9 | 9 | 9 | 9 | 8.5 | 8.5 | 8.5 | 5.5 | 5.5 | 5.5
PM | 4 | 4 | 4 | 4.7 | 5.7 | 6.2 | 6 | 6 | 5.5 | 5.5 | 5.5 | 5.5 | 4.5 | 4.5 | 4.5 | 4.5 | 3.5 | 3.5 | 3 | 3 | 3 | 2.5 | 2.5 | 2.5
Service engineer | 4 | 4 | 4 | 3 | 3 | 3 | 4.5 | 4.5 | 4.5 | 5.5 | 5.5 | 5.5 | 3.5 | 3.5 | 3.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Software engineer | 5 | 5 | 5 | 4 | 5 | 5 | 6 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6.5 | 6 | 6
SW test engineer | 3 | 3 | 3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 4.3 | 4.3 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.8 | 3.3 | 3.3 | 3.3
System engineer | 9 | 10 | 10 | 9.5 | 12 | 12 | 11.5 | 13 | 13 | 13 | 13 | 13 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 11 | 11 | 9 | 9 | 9
Tech Lead | 5.4 | 5.9 | 5.9 | 6.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 5.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4 | 4 | 4 | 3 | 3 | 3
Technician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | 40.4 | 42.9 | 42.9 | 42 | 49.5 | 51 | 53.8 | 58.3 | 57.8 | 58.8 | 59.8 | 59.8 | 52.3 | 50.3 | 50.8 | 49.8 | 48.8 | 48.8 | 46.3 | 45.3 | 45.3 | 37.8 | 37.3 | 37.3
Project Requirement
Resource Department | (All)
Status | (Multiple Items)
PJT Lifecycle | (All)
Row Labels | 합계 : 25-Nov | 합계 : 25-Dec | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | 합계 : 27-Mar | 합계 : 27-Apr | Sum of 27-May | Sum of 27-Jun | 합계 : 27-Jul | 합계 : 27-Aug | 합계 : 27-Sep | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
CatOX Alpha design | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Micron A&D | 3.5 | 7.6 | 8.7 | 10.7 | 10.7 | 8 | 8 | 8 | 6.5 | 6 | 6.5 | 6.5 | 6.5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R&D General - Legacy/TSG | 1.8 | 1.8 | 1.8 | 1.8 | 2.1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
Tumalo Ph1 | 10.8 | 10.9 | 7.6 | 7.6 | 7.4 | 6.6 | 5.6 | 5.6 | 4.9 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tumalo Ph2 | 8.1 | 8 | 9.4 | 9.4 | 9 | 7.4 | 8.4 | 8.4 | 7.4 | 7.4 | 10 | 10 | 10 | 10 | 9 | 9 | 9 | 9 | 8.5 | 8.5 | 7.5 | 7.5 | 7.5 | 1 | 1 | 1
Unify support | 1 | 1 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LPLN TOP 150 support | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kanara | 0 | 0 | 0 | 0 | 0.3 | 2.5 | 2.5 | 4 | 7.5 | 8.5 | 9.5 | 10.5 | 10.5 | 11 | 12.5 | 12.5 | 12.5 | 11.5 | 11 | 11 | 11 | 11 | 11 | 11 | 10.5 | 10.5
Hydrogen Recovery System-7N | 0 | 2.5 | 8.5 | 9 | 9.4 | 11 | 11 | 11 | 12 | 13 | 12.5 | 12.5 | 12.5 | 13 | 13.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 11 | 11 | 11 | 10 | 10 | 10
SAVAS | 0 | 0 | 0 | 0 | 0 | 1 | 8.5 | 8.5 | 10 | 13.5 | 13.5 | 13.5 | 14.5 | 14.5 | 15.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5
Grand Total | 28.7 | 34.8 | 40.4 | 42.9 | 42.9 | 42 | 49.5 | 51 | 53.8 | 58.3 | 57.8 | 58.8 | 59.8 | 59.8 | 52.3 | 50.3 | 50.8 | 49.8 | 48.8 | 48.8 | 46.3 | 45.3 | 45.3 | 37.8 | 37.3 | 37.3

## P1_정원
Total IS NPI | 48.4 | 48.4 | 48.4 | 44.4 | 45.4 | 45.4 | 45.4 | 45.4 | 45.4 | 45.4 | 45.4 | 46.4 | 46.4 | 46.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 57.4 | 47.4 | 47.4 | 0 | 0
Sustaining SW | 1.8 | 1.8 | 1.8 | 1.8 | 2.1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
Unify support SW | 0.9 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
파견 LPLN SE | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total available HC | 41.7 | 41.9 | 42.6 | 38.6 | 39.3 | 39.9 | 39.9 | 39.9 | 39.6 | 39.6 | 39.3 | 40.3 | 44.3 | 44.3 | 45.3 | 45.3 | 44.8 | 44.8 | 44.8 | 44.8 | 44.8 | 54.8 | 44.8 | 44.8 | -2.6 | -2.6
Row Labels | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-Mar | Sum of 27-Apr | Sum of 27-May | Sum of 27-Jun | Sum of 27-Jul | Sum of 27-Aug | Sum of 27-Sep | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
Control Eng. | 14.5 | 14.5 | 14.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5
Engineering | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
NPI IS | 29 | 29 | 29 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 38 | 28 | 28
PMO | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Central Engineering | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Grand Total | 48.4 | 48.4 | 48.4 | 44.4 | 45.4 | 45.4 | 45.4 | 45.4 | 45.4 | 45.4 | 45.4 | 46.4 | 46.4 | 46.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 57.4 | 47.4 | 47.4
Engineer HC | 42 | 42 | 42 | 38 | 39 | 39 | 39 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
TSG/파견 SW | 2.7 | 2.5 | 1.8 | 1.8 | 2.1 | 1.5 | 1.5 | 1.5 | 1.8 | 1.8 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6
LPLN 파견 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Available Engineer HC | 35.3 | 35.5 | 36.2 | 32.2 | 32.9 | 33.5 | 33.5 | 36.5 | 36.2 | 36.2 | 35.9 | 35.9 | 39.9 | 39.9 | 39.9 | 39.9 | 39.4 | 39.4 | 39.4 | 39.4 | 39.4 | 39.4 | 39.4 | 39.4
Resource role - engineering only
Row Labels | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-Mar | Sum of 27-Apr | Sum of 27-May | Sum of 27-Jun | Sum of 27-Jul | Sum of 27-Aug | Sum of 27-Sep | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
Electrical engineer | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Mechanical engineer | 7 | 7 | 7 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
PM | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Service engineer | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 13 | 3 | 3
Software engineer | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SW test engineer | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
System engineer | 10 | 10 | 10 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Tech Lead | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Technician
Grand Total | 42 | 42 | 42 | 38 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 40 | 40 | 40 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 51 | 41 | 41
Resource role - All
Row Labels | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-Mar | Sum of 27-Apr | Sum of 27-May | Sum of 27-Jun | Sum of 27-Jul | Sum of 27-Aug | Sum of 27-Sep | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
Control Eng. | 14.5 | 14.5 | 14.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5
Engineering | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
NPI IS | 29 | 29 | 29 | 26 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 38 | 28 | 28
PMO | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Grand Total | 47.9 | 47.9 | 47.9 | 43.9 | 44.9 | 44.9 | 44.9 | 44.9 | 44.9 | 44.9 | 44.9 | 45.9 | 45.9 | 45.9 | 46.9 | 46.9 | 46.9 | 46.9 | 46.9 | 46.9 | 46.9 | 56.9 | 46.9 | 46.9
Available HCs for IS Projects
Status
Row Labels | Sum of 26-Jan | Sum of 26-Feb | Sum of 26-Mar | Sum of 26-Apr | Sum of 26-May | Sum of 26-Jun | Sum of 26-Jul | Sum of 26-Aug | Sum of 26-Sep | Sum of 26-Oct | Sum of 26-Nov | Sum of 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-Mar | Sum of 27-Apr | Sum of 27-May
Central Engineering | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Control Eng. | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5
Engineering | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
NPI IS | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
PMO | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Grand Total | 38.4 | 38.4 | 38.4 | 38.4 | 38.4 | 38.4 | 38.4 | 38.4 | 38.4 | 38.4 | 38.4 | 38.4 | 37.9 | 37.9 | 37.9 | 37.9 | 37.9

## P2_부서
정원 - Plan | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-May | Sum of 27-Jun | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec | 0 | 0
Control Eng. | -1.1 | -1 | -0.7 | -1.3 | -3.6 | -3.6 | -4.6 | -5.6 | -5.5 | -5.5 | -6.5 | -6.5 | -5.6 | -5.8 | -5.3 | -5.3 | -2.75 | -2.25 | -2.25 | 14.5 | 14.5
Engineering | 0.1 | 0 | 0 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | -0.1 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.4 | 0.4
NPI IS | 3.9 | 1.1 | 1.1 | -1.2 | -4.9 | -5.9 | -7.9 | -11.4 | -11.4 | -12.4 | -12.4 | -11.4 | -4.9 | -2.9 | -1.9 | -2 | 6.8 | 6.8 | 6.8 | 28 | 28
PMO | -0.8 | -1 | -1 | -1.9 | -2.9 | -3.4 | -3.2 | -3.2 | -2.7 | -2.7 | -2.7 | -2.7 | -1.4 | -1.4 | -0.4 | -0.4 | 1 | 1 | 1 | 4 | 4
Central Engineering | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| 2.4 | -0.6 | -0.3 | -4.2 | -11.2 | -12.7 | -15.5 | -20 | -19.4 | -20.4 | -21.4 | -20.4 | -11.4 | -9.6 | -7.1 | -7.2 | 5.65 | 6.15 | 6.15
Status | (Multiple Items)
Row Labels | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-May | Sum of 27-Jun | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
Control Eng. | 15.6 | 15.5 | 15.2 | 14.8 | 17.1 | 17.1 | 18.1 | 19.1 | 19 | 19 | 20 | 20 | 19.1 | 19.3 | 19.8 | 19.8 | 17.25 | 16.75 | 16.75
Engineering | 0.3 | 0.4 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3 | 0.3 | 0.3
NPI IS | 25.1 | 27.9 | 27.9 | 27.2 | 31.9 | 32.9 | 34.9 | 38.4 | 38.4 | 39.4 | 39.4 | 39.4 | 32.9 | 30.9 | 29.9 | 30 | 21.2 | 21.2 | 21.2
PMO | 4.8 | 5 | 5 | 5.9 | 6.9 | 7.4 | 7.2 | 7.2 | 6.7 | 6.7 | 6.7 | 6.7 | 5.4 | 5.4 | 4.4 | 4.4 | 3 | 3 | 3
Central Engineering | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | 46 | 49 | 48.7 | 48.6 | 56.6 | 58.1 | 60.9 | 65.4 | 64.8 | 65.8 | 66.8 | 66.8 | 57.8 | 56 | 54.5 | 54.6 | 41.75 | 41.25 | 41.25

## P4_Name
Status | (Multiple Items)
Resource Department | (Multiple Items)
Row Labels | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | 합계 : 27-Jan | 합계 : 27-Feb | 합계 : 27-Mar | 합계 : 27-Apr | 합계 : 27-May | 합계 : 27-Jun | 합계 : 27-Jul | 합계 : 27-Aug | 합계 : 27-Sep | 합계 : 27-Oct | 합계 : 27-Nov | 합계 : 27-Dec
* Manager | 2.4 | 2.9 | 2.8 | 3.4 | 3.5 | 3.5 | 3.5 | 3.5 | 3.4 | 3.4 | 3.4 | 3.4 | 2.6 | 2.7 | 2.7 | 2.7 | 2.7 | 2.8 | 2.4 | 2.1 | 2.1 | 1.8 | 1.8 | 1.8
Electrical | 5.9 | 6 | 6 | 6 | 7.1 | 7.1 | 7.1 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.4 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 6.3 | 6.2 | 6.2 | 6.35 | 6.35 | 6.35
Mechanical | 5.9 | 7 | 7 | 7 | 8.2 | 9.2 | 10.2 | 12.2 | 12.2 | 12.2 | 12.2 | 12.2 | 11 | 10 | 10 | 10 | 10 | 10 | 9.3 | 9.2 | 9.2 | 6.1 | 6.1 | 6.1
PM | 4 | 4 | 4 | 4.7 | 5.7 | 6.2 | 6 | 6 | 5.5 | 5.5 | 5.5 | 5.5 | 4.5 | 4.5 | 4.5 | 4.5 | 3.5 | 3.5 | 3 | 3 | 3 | 2.5 | 2.5 | 2.5
Software | 9.2 | 9 | 8.8 | 8.3 | 9.4 | 9.4 | 10.4 | 10.9 | 10.9 | 10.9 | 11.9 | 11.9 | 11.3 | 11.3 | 11.8 | 11.8 | 11.8 | 11.8 | 11.8 | 11.6 | 11.6 | 10.5 | 10 | 10
System 1 | 5.5 | 6 | 6 | 6.5 | 10 | 10 | 11.5 | 13 | 13 | 14 | 14 | 14 | 12 | 11 | 11 | 10 | 10 | 10 | 10 | 9 | 9 | 9 | 9 | 9
System 2 | 6 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
System 3 | 6.9 | 6.9 | 6.9 | 6.5 | 6.5 | 6.5 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2
Grand Total | 45.8 | 48.8 | 48.5 | 48.4 | 56.4 | 57.9 | 60.7 | 65.2 | 64.6 | 65.6 | 66.6 | 66.6 | 57.8 | 56 | 56.5 | 55.5 | 54.5 | 54.6 | 51.3 | 49.6 | 49.6 | 41.75 | 41.25 | 41.25

## Project IO
Do Not Change This Sheet |  | Last Update | 2025-09-09
Project | Project JO | PCAS Status | Project Lifecycle |  | Terminology of Project Lifecycle Status in SUN PMO
CatOX Alpha design | 407060 | Active | Lead |  | * Define status in terms of Start to End of Phase Gate
Ganymede support - PCCA | 407078 | Cancelled | Cancelled |  | 예) Gate0가 끝나고 Gate1까지는 "Opportunity"
Havasu | 406399 | Complete | Complete
HRS Integrates | 406403 | Do Not Use | Active
Micron A&D | 406886 | Active | Active
PCAS Pre-Gate 1 Support(SIA) | 407057 | Active | Lead
R&D General - Legacy/TSG | 406442 | Active | Complete
Tumalo Ph1 | 406437 | Active | Active
EUV Zenith Plus | 406372 | Complete | Launched
Tumalo Ph2 | 407039 | Active | Active
Unify support | 407053 | Active | Planning
Carl Zeiss | TBC | Cancelled | Lead
CatOX | TBC | potential | Lead
HRS 9N Upgarde | TBC | potential | Lead
Kanara | 406376 | Active | Opportunty
Hydrogen Recovery System-7N | 407343 | Active | Active |  | Projedt Status 정의 - PCAS IS NPI 기준
Hermes | 407110 | Cancelled | Cancelled | Decision made on 2025.10 | Active | PCP에 의해 승인받고 IS NPI에서 진행하고 있는 commit project - Current product 지원 포함
Gen3 EUV Zenith Plus 7SRC TSMC | 407140 | Complete | ETO |  | Complete | 완료된 project - Gate6 or Gate5 pass로 TSG hand-over가 완료된 project
Pre CPR for IS | 407057 | Active | Opportunty |  | Plan | Pre-Gate1(Gate2) 로 NPI Project 시작 전 PCAS NPI에서 project(support) 진행을 협의 및 검토 중인 단계
LPLN TOP 150 support | 407154 | Active | Active |  | Potential | Gate0 단계 혹은 RFQ 단계의 project로 NPI 에서 진행하는 것이 협의되지 않은 상태의 모든 project or support
SAVAS | TBC | Plan | Lead

## 정원
| 정원 | [6 empty] | SuM | 47.9 | 47.9 | 48.9 | 47.9 | 47.9 | 46.9 | 46.9 | 48.4 | 48.4 | 48.4 | 44.4 | 45.4 | 45.4 | 45.4 | 45.4 | 45.4 | 45.4 | 45.4 | 46.4 | 46.4 | 46.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 57.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4 | 47.4
No | Status | Project | Name | Resource Department | Sub-Team | Resource Role | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 |  | 정원 | JiYoung Son | Engineering | * Manager | * Eng Manager |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
2 |  | 정원 | Jinney Lee | PMO | * Manager | * Manager |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 |  | 정원 | Eugene Lee | PMO | PM | PM |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4 |  | 정원 | Evan Lee | PMO | PM | PM |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 |  | 정원 | Yuro Lee | PMO | PM | PM |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 |  | 정원 | Dorothy Noh | NPI IS | * Manager | * Manager |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 |  | 정원 | Michael Kim | NPI IS | System 1 | Tech Lead |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
8 |  | 정원 | Anders You | NPI IS | System 1 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | Move | 정원 | Robin Park | NPI IS | System 1 | Technician |  |  | 1 | 1 | 1 | 1
10 | Assignment | 정원 | Ricky Kim | NPI IS | System 1 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
11 |  | 정원 | Chloe Jeong | NPI IS | System 1 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
12 | Assignment | 정원 | Judy Lee | NPI IS | System 1 | Service engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
13 | Assignment | 정원 | Chan Hwang | NPI IS | System 1 | Service engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
14 |  | 정원 | Jacob Lee | NPI IS | System 3 | Tech Lead |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
15 | Assignment | 정원 | Grace Ji | NPI IS | System 3 | Tech Lead |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
16 |  | 정원 | Noah Yeom | NPI IS | System 3 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
17 | Parental leave | 정원 | Tred Park | NPI IS | System 3 | System engineer | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
18 |  | 정원 | William Lee | NPI IS | System 3 | Tech Lead |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
19 |  | 정원 | Alyssa Park | NPI IS | System 3 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
20 | resignation | 정원 | Fred Lee | NPI IS | System 3 | Service engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
21 |  | 정원 | Chad Seo | NPI IS | System 2 | Tech Lead |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
22 |  | 정원 | Jess Kim | NPI IS | System 2 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
23 |  | 정원 | Kevin Ko | NPI IS | System 2 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
24 |  | 정원 | Emma Kim | NPI IS | System 2 | Tech Lead |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25 |  | 정원 | Harry Kwak | NPI IS | System 2 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
26 | Parental leave | 정원 | Stella Lim | NPI IS | System 2 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
27 |  | 정원 | Sophie Kim | NPI IS | System 2 | Service engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
28 |  | 정원 | Jeremy Park | NPI IS | Mechanical | Leader |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
29 |  | 정원 | Allie Park | NPI IS | Mechanical | Mechanical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
30 |  | 정원 | Wayne Jo | NPI IS | Mechanical | Mechanical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
31 |  | 정원 | Jiny Park | NPI IS | Mechanical | Mechanical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
32 | Move | 정원 | Evan Yu | NPI IS | Mechanical | Mechanical engineer |  |  | 1 | 1 | 1
33 | Parental leave | 정원 | Jayce Park | NPI IS | Mechanical | Mechanical engineer | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
34 | Parental leave | 정원 | Esther Jeong | NPI IS | Mechanical | Mechanical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
35 |  | 정원 | Sooyoung Song | NPI IS | Mechanical | Mechanical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
36 |  | 정원 | Derek Cho | NPI IS | Mechanical | Mechanical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
37 |  | 정원 | Jayden Lee | NPI IS | Mechanical | Mechanical engineer |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
38 |  | 정원 | Mogen Seo | Control Eng. | * Manager | * Manager |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
39 |  | 정원 | Gerald Park | Control Eng. | Software | Leader |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
40 | Parental leave | 정원 | Ashley Yun | Control Eng. | Software | Software engineer |  |  | 1 | 1 | 1 | 1 | 1 | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
41 |  | 정원 | Ethan Jung | Control Eng. | Software | Software engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
42 |  | 정원 | Rachel Bae | Control Eng. | Software | Software engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
43 |  | 정원 | Dave Kim | Control Eng. | Software | SW test engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
44 |  | 정원 | Moonsu Cho | Control Eng. | Software | SW test engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
45 | TSG | 정원 | Amelia An | Control Eng. | Software | SW test engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
46 |  | 정원 | Owen Rim | Control Eng. | Software | Software engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
47 | resignation | 정원 | Roy Choi | Control Eng. | Software | Software engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
48 |  | 정원 | Joshua Im | Control Eng. | Electrical | Leader |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
49 |  | 정원 | Andy Jang | Control Eng. | Electrical | Electrical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
50 |  | 정원 | May Kwon | Control Eng. | Electrical | Electrical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
51 |  | 정원 | Dean Choi | Control Eng. | Electrical | Electrical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
52 |  | 정원 | Hana Lee | Control Eng. | Electrical | Electrical engineer | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
53 |  | 정원 | Julia Mun | Control Eng. | Electrical | Electrical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
54 |  | 정원 | Victor Do | Central Engineering | Reliability | Reliability lead | [9 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
초안용 범례 (검은선 위쪽에 정원 등록 요망, 행 삽입/삭제 가능)
|  |  | Gate plan | - | - | -
|  |  | Project Manager | PMO | PM | PM
|  |  | Tech Lead | NPI IS | System 1 | Tech Lead
|  |  | System engineer | NPI IS | System 1 | System engineer
|  |  | Service engineer | NPI IS | System 1 | Service engineer
|  |  | Mechanical engineer | NPI IS | Mechanical | Mechanical engineer
|  |  | Software engineer | Control Eng. | Software | Software engineer
|  |  | SW test engineer | Control Eng. | Software | SW test engineer
|  |  | Electrical engineer | Control Eng. | Electrical | Electrical engineer
Note on B14: Noh, Dorothy (MinKyeong): 2026/1월~ PMO AA 지원
Note on B22: Noh, Dorothy (MinKyeong): 2026-03 퇴사
Note on B35: Noh, Dorothy (MinKyeong): 7월복귀 --> 5월 복귀로 변경 (260312)
Note on B49: [스레드 댓글] 사용 중인 버전의 Excel에서 이 스레드 댓글을 읽을 수 있지만 파일을 이후 버전의 Excel에서 열면 편집 내용이 모두 제거됩니다. 자세한 정보: https://go.microsoft.com/fwlink/?linkid=870924. 댓글: 2026 3/27 퇴사

## >
- | 정원 |  | Resource Plan | Ver. | 0 | Date | 2025-07-02
No | Status | Project | Name | Resource Department | Resource Role | Sub-Team | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28

## etc. V00
N/A | General Support |  |  | Resource Plan | Ver. | 0 | Date | 2025-07-02 | SUM | 3 | 4.3 | 5 | 4.5 | 6.5 | 6.8 | 6.3 | 6.7 | 6.5 | 6.1 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 6.1 | 6.1 | 6.1 | 6.1 | 2.1 | 2.1 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | Start | End | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Cancelled | Cancelled | Ganymede support - PCCA | NPI IS | System 1 | System engineer | System engineer
2 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | Software engineer | Ashley Yun |  |  | 0 | 0.3 | 1 | 1 | 1 | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
3 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | Software engineer | Rachel Bae |  |  | 0.7 | 0.7 | 0.7 | 0.7 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | SW test engineer | Amelia An |  |  | 1 | 1 | 0.9 | 0.7 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
5 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | Software engineer | Roy Choi |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
6 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | SW test engineer | Moonsu Cho |  |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
7 | Active | Planning | Unify support | Control Eng. | Software | Leader | Gerald Park |  |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | [6 empty] | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
8 | Active | Planning | Unify support | Control Eng. | Software | Software engineer | Rachel Bae | [6 empty] | 0.5 | 0.5 | 0.5 | 0.2 | 0.2
9 | Active | Planning | Unify support | Control Eng. | Software | SW test engineer | Amelia An |  |  |  |  | 0.1 | 0.3 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2
10 | Active | Complete | R&D General - Legacy/TSG | NPI IS | System 1 | Technician | Robin Park |  |  | 0.2 | 0.2 | 0.2 | 0.2
11 | Active | Lead | CatOX Alpha design | NPI IS | Mechanical | Mechanical engineer | Jiny Park |  |  |  | 1 | 1 | 0.5 | 0.5 | 0.5
12 | Cancelled | Cancelled | Hermes | Control Eng. | Software | Software engineer | Roy Choi
13 | Cancelled | Cancelled | Hermes | Control Eng. | Software | SW test engineer | Moonsu Cho
14 | Active | Active | LPLN TOP 150 support | NPI IS | System 3 | Tech Lead | Grace Ji | [6 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
15 | Active | Active | LPLN TOP 150 support | NPI IS | System 1 | System engineer | Ricky Kim | [6 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
16 | Active | Active | LPLN TOP 150 support | NPI IS | System 1 | Service engineer | Chan Hwang | [6 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
17 | Active | Active | LPLN TOP 150 support | NPI IS | System 1 | Service engineer | Judy Lee | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Micron A&D V00
Micron A&D | 406886 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 12.2 | 11.8 | 12.2 | 6.7 | 4.9 | 4.9 | 9 | 10.3 | 12.3 | 12.1 | 9.4 | 9.4 | 9.4 | 7.9 | 7.4 | 8 | 8 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Active | Active | Micron A&D | PMO | * Manager | * Manager | Jinney Lee | 2026-08-28 | 2026-12-18 | 0.2 | 0.2 | 0.2 | 0.25 | 0.25 | 0.25 | 0.25 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3
2 | Active | Active | Micron A&D | PMO | PM | PM | Eugene Lee | 2026-08-28 | 2026-12-18 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.1 | 0.9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 | Active | Active | Micron A&D | NPI IS | * Manager | * Manager | Dorothy Noh | 2026-08-28 | 2026-12-18 | 0.2 | 0.2 | 0.2 | 0.25 | 0.25 | 0.25 | 0.25 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3
4 | Active | Active | Micron A&D | NPI IS | Mechanical | Leader | Jeremy Park | 2026-08-28 | 2026-12-18 | 0.2 | 0.3 | 0.3 | 0.25 | 0.25 | 0.25 | 0.25 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
5 | Active | Active | Micron A&D | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2026-08-28 | 2026-12-18 | 1 | 1 | 1 | 0.5 |  |  | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
6 | Active | Active | Micron A&D | NPI IS | Mechanical | Mechanical engineer | Jiny Park | 2026-08-28 | 2026-12-18 | 0.5 |  |  | 0.5 |  |  |  | 0.5 | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 | 0.5
7 | Active | Active | Micron A&D | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | 2026-08-28 | 2026-12-18 |  |  | 1 | 0.2 |  |  | 1 | 0.5 | 1 | 1
8 | Active | Active | Micron A&D | NPI IS | System 2 | Tech Lead | Chad Seo | 2026-08-28 | 2026-12-18 | 0.9 | 0.9 | 0.9 |  |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | Active | Active | Micron A&D | NPI IS | System 2 | Tech Lead | Emma Kim | 2026-08-28 | 2026-12-18 | 1 | 1 | 1 | 0.7 | 0.1 | 0.1
10 | Active | Active | Micron A&D | NPI IS | System 2 | System engineer | Jess Kim | 2026-08-28 | 2026-12-18 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
11 | Active | Active | Micron A&D | NPI IS | System 3 | System engineer | Tred Park | 2026-08-28 | 2026-12-18 | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1
12 | Active | Active | Micron A&D | NPI IS | System 2 | System engineer | Stella Lim | 2026-08-28 | 2026-12-18 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1
13 | Active | Active | Micron A&D | NPI IS | System 2 | System engineer | Harry Kwak | 2026-08-28 | 2026-12-18 | 1 | 1 | 1 |  |  | 0.5 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5
14 | Active | Active | Micron A&D | Engineering | * Manager | * Eng Manager | JiYoung Son | 2026-08-28 | 2026-12-18 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
15 | Active | Active | Micron A&D | Control Eng. | * Manager | * Manager | Mogen Seo | 2026-08-28 | 2026-12-18 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
16 | Active | Active | Micron A&D | Control Eng. | Electrical | Leader | Joshua Im | 2026-08-28 | 2026-12-18 | 0.3 | 0.3 | 0.3 | 0.25 | 0.25 | 0.25 | 0.25 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
17 | Active | Active | Micron A&D | Control Eng. | Electrical | Electrical engineer | Dean Choi | 2026-08-28 | 2026-12-18 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
18 | Active | Active | Micron A&D | Control Eng. | Software | Leader | Gerald Park | 2026-08-28 | 2026-12-18 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1
19 | Active | Active | Micron A&D | Control Eng. | Software | Software engineer | Roy Choi | 2026-08-28 | 2026-12-18 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.3 | 0.7 | 0.7 | 0.7 | 0.7
20 | Active | Active | Micron A&D | Control Eng. | Software | SW test engineer | Moonsu Cho | 2026-08-28 | 2026-12-18 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
21 | Active | Active | Micron A&D | NPI IS | System 1 | System engineer | Chloe Jeong | 2026-08-28 | 2026-12-18 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
22 | Active | Active | Micron A&D | NPI IS | System 2 | System engineer | Kevin Ko | 2026-08-28 | 2026-12-18 | [5 empty] | 0.5
23 | Active | Active | Micron A&D | Central Engineering | Reliability | Reliability lead | Victor Do | 2026-08-28 | 2026-12-18 | [7 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
24 | Active | Active | Micron A&D | - | - | - | Gate Plan | 2026-08-28 | 2026-12-18 |  | Update | [12 empty] | G5 |  |  |  | G6
Alpha issue
HRS test 필요 시점.
Note on R9: [스레드 댓글] 사용 중인 버전의 Excel에서 이 스레드 댓글을 읽을 수 있지만 파일을 이후 버전의 Excel에서 열면 편집 내용이 모두 제거됩니다. 자세한 정보: https://go.microsoft.com/fwlink/?linkid=870924. 댓글: Include BB update

## Tumalo Ph2 V00
Tumalo Ph2 | 407039 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 0 | 5.1 | 7.6 | 9.3 | 9.5 | 9.2 | 9.2 | 10.7 | 10.7 | 10.4 | 8.8 | 9.8 | 9.8 | 8.8 | 8.8 | 11.4 | 11.4 | 11.4 | 11.4 | 10.4 | 10.4 | 10.4 | 10.4 | 9.9 | 9.9 | 8.3 | 8.3 | 8.3 | 1.25 | 1.25 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Active | Active | Tumalo Ph2 | Engineering | * Manager | * Eng Manager | Jiyoung Son | 2026-04-01 | 2026-09-28 | [7 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | Active | Active | Tumalo Ph2 | PMO | * Manager | * Manager | Jinney Lee | 2026-04-01 | 2026-09-28 |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1
3 | Active | Active | Tumalo Ph2 | PMO | PM | PM | Evan Lee | 2026-04-01 | 2026-09-28 |  | 0.5 | 0.5 | 0.8 | 0.8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
4 | Active | Active | Tumalo Ph2 | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-04-01 | 2027-09-28 |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1
5 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | Tech Lead | Jacob Lee | 2027-04-01 | 2027-09-28 |  |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.5
6 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | Tech Lead | William Lee | 2027-04-01 | 2027-09-28 |  | 0.9 | 0.9 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | Active | Active | Tumalo Ph2 | NPI IS | System 2 | System engineer | Harry Kwak | 2027-04-01 | 2027-09-28 |  |  | 0.4 | 0.4 |  |  | 0.4 | 0.3 | 0.3 | 0.3 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
8 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | System engineer | Noah Yeom | 2027-04-01 | 2027-09-28 |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | System engineer | Alyssa Park | 2027-04-01 | 2027-09-28 |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
10 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | System engineer | Anders You | 2027-04-01 | 2027-09-28 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1
11 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | Service engineer | Fred Lee | 2027-04-01 | 2027-09-28 |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
12 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | Service engineer | Chan Hwang | 2027-04-01 | 2027-09-28 |  |  | 0.4 | 0.4 | 0.5
13 | Active | Active | Tumalo Ph2 | NPI IS | System 2 | System engineer | Kevin Ko | 2027-04-01 | 2027-09-28
14 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | System engineer | Chloe Jeong | 2027-04-01 | 2027-09-28
15 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | Technician | Robin Park | 2027-04-01 | 2027-09-28
16 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Leader | Jeremy Park | 2027-04-01 | 2027-09-28 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1
17 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Allie Park | 2027-04-01 | 2027-09-28 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
18 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Wayne Jo | 2027-04-01 | 2027-09-28 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
19 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2027-04-01 | 2027-09-28 |  |  |  |  | 0.5 | 0.5
20 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-04-01 | 2027-09-28
21 | Active | Active | Tumalo Ph2 | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-04-01 | 2027-09-28 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
22 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Leader | Gerald Park | 2027-04-01 | 2027-09-28 | [7 empty] | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
23 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Software engineer | Ethan Jung | 2027-04-01 | 2027-09-28 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1
24 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Software engineer | Roy Choi | 2027-04-01 | 2027-09-28
25 | Active | Active | Tumalo Ph2 | Control Eng. | Software | SW test engineer | Dave Kim | 2027-04-01 | 2027-09-28 | [11 empty] | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
26 | Active | Active | Tumalo Ph2 | Control Eng. | Software | SW test engineer | Moonsu Cho | 2027-04-01 | 2027-09-28
27 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Software engineer | Owen Rim | 2027-04-01 | 2027-09-28 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
28 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Leader | Joshua Im | 2027-04-01 | 2027-09-28 |  | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1 | 0.25 | 0.25 | 0.25
29 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Electrical engineer | May Kwon | 2027-04-01 | 2027-09-28 |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
30 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Electrical engineer | Dean Choi | 2027-04-01 | 2027-09-28 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1
31 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Electrical engineer | Andy Jang | 2027-04-01 | 2027-09-28 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
32 | Active | Active | Tumalo Ph2 | - | - | - | Gate Plan | 2027-04-01 | 2027-09-28 |  | G2 | [6 empty] | G3 | [9 empty] | G4 | [5 empty] | G5 | [5 empty] | G6

## Tumalo Ph1 V00
Tumalo Ph1 | 406437 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 18 | 18.7 | 16.8 | 15 | 13 | 12.5 | 12.5 | 8.6 | 8.6 | 8.3 | 7.4 | 6.4 | 6.3 | 5.6 | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Active |  | Tumalo Ph1 | Engineering | * Manager | * Eng Manager | Jiyoung Son | 2026-02-01 | 2026-08-30 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
2 | Active |  | Tumalo Ph1 | PMO | * Manager | * Manager | Jinney Lee | 2026-02-01 | 2026-08-30 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
3 | Active |  | Tumalo Ph1 | PMO | PM | PM | Yuro Lee | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.7 | 0.7 | 0.7 | 0.5 | 0.5
4 | Active | Active | Tumalo Ph1 | NPI IS | * Manager | * Manager | Dorothy Noh | 2026-02-01 | 2026-08-30 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
5 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | Tech Lead | Jacob Lee | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
6 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | Tech Lead | Grace Ji | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 0.5
7 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | Tech Lead | William Lee | 2026-03-01 | 2026-09-27 |  |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
8 | Active | Active | Tumalo Ph1 | NPI IS | System 2 | System engineer | Harry Kwak | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.5 | 0.5 | 0.6 | 0.2 | 0.2 | 0.2
9 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | System engineer | Alyssa Park | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
10 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | System engineer | Noah Yeom | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
11 | Active | Active | Tumalo Ph1 | NPI IS | System 1 | System engineer | Anders You | 2026-02-01 | 2026-08-30 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
12 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | Service engineer | Fred Lee | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
13 | Active | Active | Tumalo Ph1 | NPI IS | System 1 | Service engineer | Chan Hwang | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6
14 | Active | Active | Tumalo Ph1 | NPI IS | System 1 | Technician | Robin Park | 2026-02-01 | 2026-08-30 | 0.8 | 0.8 | 0.8 | 0.8
15 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Leader | Jeremy Park | 2026-02-01 | 2026-08-30 | 0.3 | 0.3 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1
16 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Mechanical engineer | Evan Yu | 2026-02-01 | 2026-08-30 | 1 | 1 | 1
17 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Mechanical engineer | Wayne Jo | 2026-02-01 | 2026-08-30 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
18 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Mechanical engineer | Esther Jeong | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1
19 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Mechanical engineer | Allie Park | 2026-02-01 | 2026-08-30 | [9 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
20 | Active | Active | Tumalo Ph1 | Control Eng. | * Manager | * Manager | Mogen Seo | 2026-02-01 | 2026-08-30 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
21 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Leader | Gerald Park | 2026-02-01 | 2026-08-30 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
22 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Ethan Jung | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1
23 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Roy Choi | 2026-02-01 | 2026-08-30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
24 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Ashley Yun | 2026-02-01 | 2026-08-30 |  |  |  |  | 0 | 0 | 0
25 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Rachel Bae | 2026-02-01 | 2026-08-30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3
26 | Active | Active | Tumalo Ph1 | Control Eng. | Software | SW test engineer | Dave Kim | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
27 | Active | Active | Tumalo Ph1 | Control Eng. | Software | SW test engineer | Moonsu Cho | 2026-02-01 | 2026-08-30
28 | Active | Active | Tumalo Ph1 | Control Eng. | Software | SW test engineer | Amelia An | 2026-02-01 | 2026-08-30 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
29 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Leader | Joshua Im | 2026-02-01 | 2026-08-30 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
30 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Electrical engineer | May Kwon | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.5
31 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Electrical engineer | Julia Mun | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5
32 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Electrical engineer | Andy Jang | 2026-02-01 | 2026-08-30
33 | Active | Active | Tumalo Ph1 | - | - | - | Gate Plan | 2026-02-01 | 2026-08-30 |  |  | G4 | [5 empty] | G5 | [5 empty] | G6
Note on T21: [스레드 댓글] 사용 중인 버전의 Excel에서 이 스레드 댓글을 읽을 수 있지만 파일을 이후 버전의 Excel에서 열면 편집 내용이 모두 제거됩니다. 자세한 정보: https://go.microsoft.com/fwlink/?linkid=870924. 댓글: PH1 ALPHA RELEASE START

## HRS
Hydrogen Recovery System-7N | 407343 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-09 | SUM | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 9.7 | 10.3 | 10.7 | 12.2 | 12.2 | 12.2 | 13.2 | 14.2 | 13.7 | 13.7 | 13.7 | 14.2 | 14.7 | 13.7 | 13.7 | 13.7 | 13.7 | 13.7 | 12.2 | 11.8 | 11.8 | 10.8 | 10.8 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | PJT Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Active | Active | Hydrogen Recovery System-7N | Engineering | * Manager | * Eng Manager | JiYoung Son | [9 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | Active | Active | Hydrogen Recovery System-7N | PMO | * Manager | * Manager | Jinney Lee | [9 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
3 | Active | Active | Hydrogen Recovery System-7N | PMO | PM | PM | Yuro Lee | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
4 | Active | Active | Hydrogen Recovery System-7N | NPI IS | * Manager | * Manager | Dorothy Noh | [9 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
5 | Active | Active | Hydrogen Recovery System-7N | NPI IS | System 2 | Tech Lead | Emma Kim | [8 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
6 | Active | Active | Hydrogen Recovery System-7N | NPI IS | System 2 | System engineer | Kevin Ko | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | Active | Active | Hydrogen Recovery System-7N | NPI IS | System 1 | System engineer | System engineer | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
8 | Active | Active | Hydrogen Recovery System-7N | NPI IS | System 2 | Service engineer | Sophie Kim | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
10 | Active | Active | Hydrogen Recovery System-7N | NPI IS | Mechanical | Leader | Jeremy Park | [8 empty] | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
11 | Active | Active | Hydrogen Recovery System-7N | NPI IS | Mechanical | Mechanical engineer | Sooyoung Song | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
12 | Active | Active | Hydrogen Recovery System-7N | NPI IS | Mechanical | Mechanical engineer | Jiny Park | [8 empty] | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5
13 | Active | Active | Hydrogen Recovery System-7N | NPI IS | Mechanical | Mechanical engineer | Jayce Park | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
14 | Active | Active | Hydrogen Recovery System-7N | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer
15 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | * Manager | * Manager | Mogen Seo | [9 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
16 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | Software | Leader | Gerald Park | [9 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
17 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | Software | Software engineer | Software engineer | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
18 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | Software | SW test engineer | Moonsu Cho | [11 empty] | 0.2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
19 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | Electrical | Leader | Joshua Im | [9 empty] | 0.2 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
20 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | Electrical | Electrical engineer | Hana Lee | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
21 | Active | Active | Hydrogen Recovery System-7N | NPI IS | System 2 | System engineer | Harry Kwak | [9 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
22 | Active | Active | Hydrogen Recovery System-7N | NPI IS | System 1 | Tech Lead | Michael Kim | [9 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
23 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | Software | Software engineer | Owen Rim | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
24 | Active | Active | Hydrogen Recovery System-7N | Control Eng. | Software | SW test engineer | Amelia An | [11 empty] | 0.2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
25 | Active | Active | Hydrogen Recovery System-7N | - | - | - | Gate Plan | 7N |  | G2 |  |  | G5 | [9 empty] | G3 | [5 empty] | G5 | [5 empty] | G6
26 | Active | Active | Hydrogen Recovery System-7N | - | - | - | Gate Plan | 9N | [14 empty] | G3 | Build | Test | Test |  |  | G4 |  |  |  |  | G5 | [5 empty] | G6
Note on Z13: [스레드 댓글] 사용 중인 버전의 Excel에서 이 스레드 댓글을 읽을 수 있지만 파일을 이후 버전의 Excel에서 열면 편집 내용이 모두 제거됩니다. 자세한 정보: https://go.microsoft.com/fwlink/?linkid=870924. 댓글: H2D-HPD ALPHA RELEASE

## Kanara V00
Kanara | 406376 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 1.1 | 3.8 | 3.8 | 5.4 | 8.9 | 9.9 | 11.1 | 12.1 | 12.1 | 12.6 | 14.1 | 14.1 | 14.1 | 13.1 | 12.6 | 12.6 | 12.4 | 12.2 | 12.2 | 12.2 | 11.7 | 11.7 | 10.3 | 10.3 | 10.3 | 10.3 | 9.8 | 9.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Active | Opportunty | Kanara | Engineering | * Manager | * Eng Manager | JiYoung Son | 2027-07-30 | 2027-12-27 | [8 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | Active | Opportunty | Kanara | PMO | * Manager | * Manager | Jinney Lee | 2027-07-30 | 2027-12-27 | [8 empty] | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
3 | Active | Opportunty | Kanara | PMO | PM | PM | Project manager | 2027-07-30 | 2027-12-27 | [9 empty] | 0.3 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
4 | Active | Opportunty | Kanara | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-07-30 | 2027-12-27 | [8 empty] | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
5 | Active | Opportunty | Kanara | NPI IS | System 3 | Tech Lead | Jacob Lee | 2027-07-30 | 2027-12-27 | [10 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | Active | Opportunty | Kanara | NPI IS | System 3 | System engineer | Tred Park | 2027-07-30 | 2027-12-27 | [10 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | Active | Opportunty | Kanara | NPI IS | System 1 | System engineer | System engineer | 2027-07-30 | 2027-12-27 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
8 | Active | Opportunty | Kanara | NPI IS | System 1 | System engineer | Chloe Jeong | 2027-07-30 | 2027-12-27 | [13 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | Active | Opportunty | Kanara | NPI IS | System 1 | Service engineer | Service engineer | 2027-07-30 | 2027-12-27 | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1
11 | Active | Opportunty | Kanara | NPI IS | Mechanical | Leader | Jeremy Park | 2027-07-30 | 2027-12-27 | [8 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
12 | Active | Opportunty | Kanara | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | 2027-07-30 | 2027-12-27 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
13 | Active | Opportunty | Kanara | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2027-07-30 | 2027-12-27 | [18 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
14 | Active | Opportunty | Kanara | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-07-30 | 2027-12-27 | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
15 | Active | Opportunty | Kanara | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-07-30 | 2027-12-27 | [10 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
16 | Active | Opportunty | Kanara | Control Eng. | Software | Leader | Gerald Park | 2027-07-30 | 2027-12-27 | [10 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
17 | Active | Opportunty | Kanara | Control Eng. | Software | Software engineer | Ethan Jung | 2027-07-30 | 2027-12-27 | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
18 | Active | Opportunty | Kanara | Control Eng. | Software | SW test engineer | Dave Kim | 2027-07-30 | 2027-12-27 | [15 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
19 | Active | Opportunty | Kanara | Control Eng. | Electrical | Leader | Joshua Im | 2027-07-30 | 2027-12-27 | [10 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
20 | Active | Opportunty | Kanara | Control Eng. | Electrical | Electrical engineer | Julia Mun | 2027-07-30 | 2027-12-27 | [13 empty] | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
21 | Active | Opportunty | Kanara | Control Eng. | Electrical | Electrical engineer | Andy Jang | 2027-07-30 | 2027-12-27 | [14 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
17 | Active | Opportunty | Kanara | Control Eng. | Software | Software engineer | Software engineer | 2027-07-30 | 2027-12-27 | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
23 | Active | Opportunty | Kanara | - | - | - | Gate Plan | 2027-07-30 | 2027-12-27 | [8 empty] | G1 |  |  |  |  | G2 |  |  |  |  | G3 | [6 empty] | G4 |  |  |  |  | G5 | [5 empty] | G6

## SAVAS
SAVAS | TBC |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 9.5 | 9.5 | 11 | 14.5 | 14.5 | 14.5 | 15.5 | 15.5 | 16.5 | 15.7 | 15.7 | 15.7 | 15.7 | 15.8 | 15.8 | 14.2 | 14.2 | 14.4 | 14.4 | 14.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Plan | Lead | SAVAS | Engineering | * Manager | * Eng Manager | JiYoung Son | 2027-06-01 | 2027-12-01 | [10 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | Plan | Lead | SAVAS | PMO | * Manager | * Manager | Jinney Lee | 2027-06-01 | 2027-12-01 | [10 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
3 | Plan | Lead | SAVAS | PMO | PM | PM | Project Manager | 2027-06-01 | 2027-12-01 | [10 empty] | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
4 | Plan | Lead | SAVAS | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-06-01 | 2027-12-01 | [10 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
5 | Plan | Lead | SAVAS | NPI IS | System 1 | Tech Lead | Tech Lead | 2027-06-01 | 2027-12-01 | [10 empty] | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
6 | Plan | Lead | SAVAS | NPI IS | System 1 | System engineer | System engineer | 2027-06-01 | 2027-12-01 | [11 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
7 | Plan | Lead | SAVAS | NPI IS | System 1 | System engineer | System engineer | 2027-06-01 | 2027-12-01 | [11 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
8 | Plan | Lead | SAVAS | NPI IS | System 1 | System engineer | System engineer | 2027-06-01 | 2027-12-01 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | Plan | Lead | SAVAS | NPI IS | System 1 | Service engineer | Service engineer | 2027-06-01 | 2027-12-01 | [13 empty] | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
10 | Plan | Lead | SAVAS | NPI IS | Mechanical | Leader | Jeremy Park | 2027-06-01 | 2027-12-01 | [11 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
11 | Plan | Lead | SAVAS | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-06-01 | 2027-12-01 | [11 empty] | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
12 | Plan | Lead | SAVAS | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-06-01 | 2027-12-01 | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1
13 | Plan | Lead | SAVAS | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-06-01 | 2027-12-01 | [11 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2
14 | Plan | Lead | SAVAS | Control Eng. | Software | Leader | Gerald Park | 2027-06-01 | 2027-12-01 | [11 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2
15 | Plan | Lead | SAVAS | Control Eng. | Software | Software engineer | Software engineer | 2027-06-01 | 2027-12-01 | [11 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
16 | Plan | Lead | SAVAS | Control Eng. | Software | Software engineer | Software engineer | 2027-06-01 | 2027-12-01 | [14 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
17 | Plan | Lead | SAVAS | Control Eng. | Software | SW test engineer | SW test engineer | 2027-06-01 | 2027-12-01 | [17 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
18 | Plan | Lead | SAVAS | Control Eng. | Electrical | Leader | Joshua Im | 2027-06-01 | 2027-12-01 | [11 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
19 | Plan | Lead | SAVAS | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2027-06-01 | 2027-12-01 | [11 empty] | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
20 | Plan | Lead | SAVAS | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2027-06-01 | 2027-12-01
21 | Plan | Lead | SAVAS | - | - | - | Gate Plan | 2027-06-01 | 2027-12-01 | [10 empty] | G1 |  |  | G2 |  |  |  |  | G3 | [6 empty] | G5 |  |  |  |  | G6
장비 만드는 비용
compliance
test equipment
service tooling?

## HRS Integrated- 9N Upgrade V00
HRS 9N Upgarde | TBC |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6 | 4.6 | 5.6 | 6.1 | 7.6 | 7.6 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | potential | Lead | HRS 9N Upgarde | PMO | * Manager | * Manager | Jinney Lee | 2027-01-25 | 2027-01-25 | [19 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
2 | potential | Lead | HRS 9N Upgarde | PMO | PM | PM | Eugene Lee | 2027-01-25 | 2027-01-25 | [19 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 | potential | Lead | HRS 9N Upgarde | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-01-25 | 2027-01-25 | [19 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
4 | potential | Lead | HRS 9N Upgarde | NPI IS | System 2 | Tech Lead | Chad Seo | 2027-01-25 | 2027-01-25 | [21 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 | potential | Lead | HRS 9N Upgarde | NPI IS | System 1 | System engineer | Anders You | 2027-01-25 | 2027-01-25 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | potential | Lead | HRS 9N Upgarde | NPI IS | System 3 | Service engineer | Fred Lee | 2027-01-25 | 2027-01-25 | [19 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
7 | potential | Lead | HRS 9N Upgarde | NPI IS | Mechanical | Leader | Jeremy Park | 2027-01-25 | 2027-01-25 | [19 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
8 | potential | Lead | HRS 9N Upgarde | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2027-01-25 | 2027-01-25 | [19 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | potential | Lead | HRS 9N Upgarde | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-01-25 | 2027-01-25 | [19 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
10 | potential | Lead | HRS 9N Upgarde | Control Eng. | Software | Leader | Gerald Park | 2027-01-25 | 2027-01-25 | [23 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
11 | potential | Lead | HRS 9N Upgarde | Control Eng. | Software | Software engineer | Software engineer | 2027-01-25 | 2027-01-25 | [19 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
12 | potential | Lead | HRS 9N Upgarde | Control Eng. | Software | SW test engineer | SW test engineer | 2027-01-25 | 2027-01-25 | [23 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
13 | potential | Lead | HRS 9N Upgarde | Control Eng. | Electrical | Leader | Joshua Im | 2027-01-25 | 2027-01-25 | [19 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
14 | potential | Lead | HRS 9N Upgarde | Control Eng. | Electrical | Electrical engineer | Dean Choi | 2027-01-25 | 2027-01-25 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
15 | potential | Lead | HRS 9N Upgarde | - | - | - | Gate Plan | 2027-01-25 | 2027-01-25 | [19 empty] | G2 | [5 empty] | Update |  |  |  |  | G5/G6

## CatOX V00
CatOX | TBC |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8 | 7.8 | 7.8 | 7.8 | 10.9 | 10.9 | 12.3 | 13.3 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.2 | 13.1 | 13.1 | 13.1 | 13.1 | 13.1 | 12.5 | 11.4 | 11.4 | 11.4 | 11.4
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | potential | Lead | CatOX | Engineering | * Manager | * Eng Manager | JiYoung Son | 2027-06-01 | 2027-12-01 | [19 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | potential | Lead | CatOX | PMO | * Manager | * Manager | Jinney Lee | 2027-06-01 | 2027-12-01 | [19 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1
3 | potential | Lead | CatOX | PMO | PM | PM | Yuro Lee | 2027-06-01 | 2027-12-01 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4 | potential | Lead | CatOX | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-06-01 | 2027-12-01 | [19 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
5 | potential | Lead | CatOX | NPI IS | System 1 | Tech Lead | Michael Kim | 2027-06-01 | 2027-12-01 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | potential | Lead | CatOX | NPI IS | System 1 | System engineer | System engineer | 2027-06-01 | 2027-12-01 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | potential | Lead | CatOX | NPI IS | System 1 | System engineer | System engineer | 2027-06-01 | 2027-12-01 | [19 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
8 | potential | Lead | CatOX | NPI IS | System 1 | System engineer | System engineer | 2027-06-01 | 2027-12-01 | [23 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | potential | Lead | CatOX | NPI IS | System 1 | Service engineer | Service engineer | 2027-06-01 | 2027-12-01 | [25 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
10 | potential | Lead | CatOX | NPI IS | Mechanical | Leader | Jeremy Park | 2027-06-01 | 2027-12-01 | [19 empty] | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
11 | potential | Lead | CatOX | NPI IS | Mechanical | Mechanical engineer | Jiny Park | 2027-06-01 | 2027-12-01 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
12 | potential | Lead | CatOX | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-06-01 | 2027-12-01 | [23 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
13 | potential | Lead | CatOX | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-06-01 | 2027-12-01 | [19 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
14 | potential | Lead | CatOX | Control Eng. | Software | Leader | Gerald Park | 2027-06-01 | 2027-12-01 | [19 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
15 | potential | Lead | CatOX | Control Eng. | Software | Software engineer | Software engineer | 2027-06-01 | 2027-12-01 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
16 | potential | Lead | CatOX | Control Eng. | Software | Software engineer | Software engineer | 2027-06-01 | 2027-12-01 | [19 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
17 | potential | Lead | CatOX | Control Eng. | Software | SW test engineer | SW test engineer | 2027-06-01 | 2027-12-01 | [26 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
18 | potential | Lead | CatOX | Control Eng. | Electrical | Leader | Joshua Im | 2027-06-01 | 2027-12-01 | [19 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
19 | potential | Lead | CatOX | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2027-06-01 | 2027-12-01 | [19 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
20 | potential | Lead | CatOX | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2027-06-01 | 2027-12-01 | [25 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
21 | potential | Lead | CatOX | - | - | - | Gate Plan | 2027-06-01 | 2027-12-01 | [20 empty] | G1 |  | G2 |  |  |  | G3 |  |  |  |  | G4 | [5 empty] | G5 | [5 empty] | G6

## HRS Integrates V00
HRS Integrates | 406403 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 0.5 | 0.5 | 0.5 | 1.3 | 5.3 | 5.1 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Do Not Use | Active | HRS Integrates | PMO | * Manager | * Manager | Jinney Lee | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3
2 | Do Not Use | Active | HRS Integrates | PMO | PM | PM | Eugene Lee | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.9 | 0.1
3 | Do Not Use | Active | HRS Integrates | NPI IS | * Manager | * Manager | Dorothy Noh | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3
4 | Do Not Use | Active | HRS Integrates | NPI IS | System 2 | Tech Lead | Chad Seo | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1
5 | Do Not Use | Active | HRS Integrates | NPI IS | System 3 | Tech Lead | William Lee | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
6 | Do Not Use | Active | HRS Integrates | NPI IS | System 2 | Tech Lead | Emma Kim | 2026-03-30 | 2026-03-30 |  |  |  | 0.3 | 0.9 | 0.9 | 0.5
7 | Do Not Use | Active | HRS Integrates | NPI IS | System 2 | Service engineer | Sophie Kim | 2026-03-30 | 2026-03-30 |  |  |  | 0.3 | 1 | 0.5 | 1
8 | Do Not Use | Active | HRS Integrates | NPI IS | System 2 | System engineer | Kevin Ko | [6 empty] | 1 | 0.5 | 1
9 | Do Not Use | Active | HRS Integrates | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | 2026-03-30 | 2026-03-30 |  |  |  | 0.3 | 0.5 | 0.5
10 | Do Not Use | Active | HRS Integrates | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2026-03-30 | 2026-03-30
11 | Do Not Use | Active | HRS Integrates | Control Eng. | Electrical | Electrical engineer | Dean Choi | 2026-03-30 | 2026-03-30 |  |  |  |  | 0.5 | 0.5
12 | Do Not Use | Active | HRS Integrates | Control Eng. | Software | SW test engineer | Moonsu Cho | 2026-03-30 | 2026-03-30 |  |  |  |  | 0.5 | 0.5
14 | Do Not Use | Active | HRS Integrates | NPI IS | System 2 | System engineer | Harry Kwak | [6 empty] | 0.5 | 0.5
15 | Do Not Use | Active | HRS Integrates | PMO | PM | PM | Yuro Lee | [8 empty] | 0.3
16 | Do Not Use | Active | HRS Integrates | - | - | - | Gate Plan | 2026-03-30 | 2026-03-30 | G2 | [8 empty] | G5 | [7 empty] | G5 |  |  |  | G6

## Havasu V00
Havasu | 406399 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 11.5 | 9.7 | 8.2 | 5.9 | 4.4 | 5.3 | 4.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Complete | Complete | Havasu | Engineering | * Manager | * Eng Manager | Jiyoung Son | 2025-06-25 | 2025-12-22 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | Complete | Complete | Havasu | PMO | * Manager | * Manager | Jinney Lee | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
3 | Complete | Complete | Havasu | PMO | PM | PM | Evan Lee | 2025-06-25 | 2025-12-22 | 1 | 1 | 0.5 | 0.2 | 0.2 | 0.2 | 0.1 | 0
4 | Complete | Complete | Havasu | NPI IS | * Manager | * Manager | Dorothy Noh | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
5 | Complete | Complete | Havasu | NPI IS | System 1 | Tech Lead | Michael Kim | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 0.5 | 0.5 | 0.7 | 1 | 0.5
6 | Complete | Complete | Havasu | NPI IS | System 1 | System engineer | Ricky Kim | 2025-06-25 | 2025-12-22 | 1 | 1 | 0.5 | 0.5
7 | Complete | Complete | Havasu | NPI IS | System 1 | System engineer | Anders You | 2025-06-25 | 2025-12-22 | 1 | 1 | 1
8 | Complete | Complete | Havasu | NPI IS | System 1 | System engineer | Chloe Jeong | 2025-06-25 | 2025-12-22 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1
9 | Complete | Complete | Havasu | NPI IS | System 1 | Service engineer | Judy Lee | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 0.5 | 0.5 | 0.7 | 1
10 | Complete | Complete | Havasu | NPI IS | Mechanical | Leader | Jeremy Park | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
11 | Complete | Complete | Havasu | NPI IS | Mechanical | Mechanical engineer | Sooyoung Song | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 1 | 1 | 1
13 | Complete | Complete | Havasu | Control Eng. | * Manager | * Manager | Mogen Seo | 2025-06-25 | 2025-12-22 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
14 | Complete | Complete | Havasu | Control Eng. | Software | Leader | Gerald Park | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
15 | Complete | Complete | Havasu | Control Eng. | Software | Software engineer | Roy choi | 2025-06-25 | 2025-12-22 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
16 | Complete | Complete | Havasu | Control Eng. | Software | SW test engineer | Moonsu Cho | 2025-06-25 | 2025-12-22 | 0.5 | 0.5 | 0.5 | 0.5
17 | Complete | Complete | Havasu | Control Eng. | Electrical | Leader | Joshua Im | 2025-06-25 | 2025-12-22 | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
18 | Complete | Complete | Havasu | Control Eng. | Electrical | Electrical engineer | Andy Jang | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 0.5 |  |  | 0.5 | 0.3
19 | Complete | Complete | Havasu | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2025-06-25 | 2025-12-22 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5
20 | Complete | Complete | Havasu | - | - | - | Gate plan | 2025-06-25 | 2025-12-22 | G5 | [5 empty] | G6

## Gen3 7SRC TFT
Gen3 EUV Zenith Plus 7SRC TSMC | 407140 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 0 | 0 | 0.2 | 6.4 | 5.2 | 5.2 | 2.8 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | PMO | * Manager | * Manager | Jinney Lee |  |  |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
2 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | Tech Lead | Chad Seo | [5 empty] | 1 | 1 | 1 | 0.5
3 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | * Manager | * Manager | Dorothy Noh | [5 empty] | 0.1 | 0.1 | 0.1 | 0.1
5 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | System engineer | Kevin Ko | [5 empty] | 1 | 0 | 0
6 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | Service engineer | Sophie Kim | [5 empty] | 0.7 | 0 | 0
7 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | System engineer | Jess Kim | [6 empty] | 0.5 | 0.5
8 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | Mechanical | Leader | Jeremy Park | [5 empty] | 0.1 | 0.1 | 0.1 |  | 0.1
9 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | [5 empty] | 0.5 | 0.5 | 0.5 |  | 0.5
10 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | Mechanical | Mechanical engineer | Derek Cho | [5 empty] | 0.5 |  |  |  | 0.5
11 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | * Manager | * Manager | Mogen Seo
12 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Software | Leader | Gerald Park
13 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Software | Software engineer | Ashley Yun | [5 empty] | 0.5 | 0.5 | 0.5 | 0.5
14 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Software | SW test engineer | Moonsu Cho | [5 empty] | 0.5 | 0.5 | 0.5 | 0.5
15 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Electrical | Leader | Joshua Im | [5 empty] | 0.3 | 0.3 | 0.3
16 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Electrical | Electrical engineer | Dean Choi | [5 empty] | 1 | 0.5 | 0.5
17 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 3 | System engineer | Tred Park | [6 empty] | 1 | 1 | 1
18 | Complete | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | - | - | - | Gate Plan |  |  |  |  | G2 |  |  |  | G5
Note on R11: [스레드 댓글] 사용 중인 버전의 Excel에서 이 스레드 댓글을 읽을 수 있지만 파일을 이후 버전의 Excel에서 열면 편집 내용이 모두 제거됩니다. 자세한 정보: https://go.microsoft.com/fwlink/?linkid=870924. 댓글: 7SRC ALPHA RELEASE

## EUV Zenith Plus V00
EUV Zenith Plus | 406372 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-02 | SUM | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Complete | Launched | EUV Zenith Plus | PMO | * Manager | * Manager | Jinney Lee | 2025-11-30 | 2026-06-30 | 0.2
2 | Complete | Launched | EUV Zenith Plus | PMO | PM | PM | Yuro Lee | 2025-11-30 | 2026-06-30 | 0.2
3 | Complete | Launched | EUV Zenith Plus | NPI IS | * Manager | * Manager | Dorothy Noh | 2025-11-30 | 2026-06-30 | 0.2
4 | Complete | Launched | EUV Zenith Plus | - | - | - | Gate Plan | 2025-11-30 | 2026-06-30 | G6

## Carl Zeiss. V00_Cancel
Carl Zeiss | TBC |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-09 | SUM | 0 | 0 | 0 | 0 | 4.5 | 6.5 | 8.5 | 9 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Cancelled | Lead | Carl Zeiss | PMO | * Manager | * Manager | Jinney Lee | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | Cancelled | Lead | Carl Zeiss | PMO | PM | PM | Project manager | [6 empty] | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7
3 | Cancelled | Lead | Carl Zeiss | NPI IS | * Manager | * Manager | Dorothy Noh | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
4 | Cancelled | Lead | Carl Zeiss | NPI IS | System 1 | Tech Lead | Michael Kim | [6 empty] | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 | Cancelled | Lead | Carl Zeiss | NPI IS | System 1 | System engineer | System engineer | [6 empty] | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | Cancelled | Lead | Carl Zeiss | NPI IS | System 1 | Service engineer | Judy Lee | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | Cancelled | Lead | Carl Zeiss | NPI IS | Mechanical | Leader | Jeremy Park | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
8 | Cancelled | Lead | Carl Zeiss | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | [6 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | Cancelled | Lead | Carl Zeiss | Control Eng. | * Manager | * Manager | Mogen Seo | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
10 | Cancelled | Lead | Carl Zeiss | Control Eng. | Software | Leader | Gerald Park | [6 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
11 | Cancelled | Lead | Carl Zeiss | Control Eng. | Software | Software engineer | Software engineer | [6 empty] | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1
12 | Cancelled | Lead | Carl Zeiss | Control Eng. | Software | SW test engineer | SW test engineer | [7 empty] | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5
13 | Cancelled | Lead | Carl Zeiss | Control Eng. | Electrical | Leader | Joshua Im | [6 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
14 | Cancelled | Lead | Carl Zeiss | Control Eng. | Electrical | Electrical engineer | Electrical engineer | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
15 | Cancelled | Lead | Carl Zeiss | - | - | - | Gate Plan | [6 empty] | G2 | [9 empty] | G5

## <
[IO No] | LPLN1 |  | Resource Plan | Ver. | 0 | Date | 2025-07-02
No | Status | Project | Name | Resource Department | Resource Role | Sub-Team | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28